## Introduction>>
Objective of the Roadmap
This roadmap represents the second phase of the project supporting Spanish market participants in their adaptation to the transition to a T+1 settlement cycle. It has been developed to guide institutions on the key deadlines and activities required to achieve readiness. It is important to note that this roadmap is an indicative tool, intended to help each institution assess and analyse its specific operational and technological preparedness for the transition. Tasks related to gap analysis, requirements definition, and implementation have been broken down for the areas of impact. This document, published on 21 November 2025, takes as reference the activities set out in the BME T+1 Playbook, the recommendations of the EU T+1 Industry Committee, and the Final Report on Amendments to the RTS on Settlement Discipline.
Structure of the document
The document has been structured into three main sheets. The following sections describe the content of each sheet and its intended purpose. 1. T+1 Spanish Market Roadmap: A calendar-based view of the activities associated with each stream — Trade Processing, Corporate Actions, Treasury, Asset Management and Documentation Management. The timeline indicates the recommended intervals for performing these activities. In addition, activities linked to a recommendation from the European Industry Committee are marked with a [«], while those related to the published Settlement Discipline RTS are marked with a [2] symbol. 2. Activities Detail: Provides a detailed description of each task, including its linkage to the functional definition phase, its alignment with EU T+1 Industry Committee recommendations and the Settlement Discipline RTS, and, within the implementation section, the identification of the systems impacted. Additionally, in the columns referring to the EU Industry Committee recommendations, those recommendations that have an associated Settlement RTS are highlighted in orange. 3. EU Recommendations: A table detailing the recommendations issued by the EU Industry Committee and their relationship to the RTS set out in the Final Report on Amendments to the RTS on Settlement Discipline.
Roadmap T+1 Spanish market
In collaboration with
Date: 21st November 2025

## 1. Roadmap T+1 Spanish market
Procceses and Activities
|  |  | 2025 | 2026 | [47 empty] | 2027
|  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October
|  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3
1. TRADE PROCESSING
1.2 Trading
A - Analysis GAP
| A - 1.1.1 | Real-time automation and integration | This phase should be completed during 2025 | [87 empty] | GO LIVE
| A - 1.1.2 | Anticipated liquidity management
| A - 1.1.3 | Review of procedures with the CCP
| A- 1.1.4 | Study of static data management
| A - 1.1.5 | Trading Regulations
| A - 1.1.6 | Counterparty risk management assessment
| A - 1.1.7 | Order Management Systems (OMS) Assessment
| A - 1.1.8 | System management
B - Definition of operational and technical requirements
| B - 1.1.1 | Definition of real-time automation and counterparty communication
| B - 1.1.2 | Foreign exchange (FX) management
« | B - 1.1.3 | Cut-off review
| B - 1.1.4 | Settlement instruction management (SSI)
« | B - 1.1.5 | Pre-trade monitoring and reporting
« | B - 1.1.6 | Definition of shaping parameters
C- Implementation
| C - 1.1.1 | Extend real-time STP across FO–MO–BO and enable same-day affirmation through automation, e-affirmation, and bilateral coordination with counterparties and custodians | bar: January W1 to October W3
| C - 1.1.2 | Deploy predictive intraday liquidity and collateral models, automate prefunding and FX hedging, and enable real-time reconciliation and alerts for T+1 readiness | bar: January W1 to October W3
| C - 1.1.3 | Centralize cut-offs, align windows across systems, update CCP processes with real-time fail/penalty handling, and simulate T+1 stress scenarios | bar: January W1 to October W3
| C - 1.1.4 | Consolidate and normalize SSIs and critical settlement data, apply automatic validations, and maintain full audit trails with version control | bar: January W1 to October W3
| C - 1.1.5 | Integrate T+1 pre-trade validations, update market rules and intraday limits, and deploy dashboards/KPIs to monitor allocations, confirmations, fails, and cash shortfalls | bar: January W1 to October W3
| C - 1.1.6 | Synchronize trade execution, positions, and risk in real time, calculate intraday exposures, trigger alerts for breaches/FX shortfalls, and integrate dynamic cut-off limits | bar: January W1 to October W3
| C - 1.1.7 | Connect FO–MO via bidirectional APIs and event-driven workflows, publish trade events in real time, and manage intraday exceptions with automated routing and dashboards | bar: January W1 to October W3
1.2 Trade Capture
A - Analysis GAP | [90 empty] | GO LIVE
| A - 1.2.1 | Evaluation of current deadlines | This phase should be completed during 2025
| A - 1.2.2 | Analysis of late or erroneous allocations and confirmations
| A - 1.2.3 | Analysis of the degree of automation
| A - 1.2.4 | Review of accounts assigned by default
| A - 1.2.5 | Analysis of standardization and quality of SSIs
| A - 1.2.6 | Study of interaction with external counterparties and clients
| A - 1.2.7 | Evaluation of messaging and communication formats
| A - 1.2.8 | Review of the onboarding process and management of static customer data
| A - 1.2.9 | Exception control analysis and discrepancy resolution
B - Definition of operational and technical requirements
«2 | B - 1.2.1 | Definition of requirements regarding new deadlines
| B - 1.2.2 | Defining requirements to increase automation of allocation and confirmation
«2 | B - 1.2.3 | Definition of requirements for interaction with external counterparties or third parties and clients
«2 | B - 1.2.4 | Definition of requirements for the standardization and quality of SSIs
«2 | B - 1.2.5 | Definition of requirements for messaging and communication formats
«2 | B - 1.2.6 | Defining requirements for onboarding and managing static customer data
«2 | B - 1.2.7 | Definition of requirements for the PSET
C- Implementation
| C - 1.2.1 | Reconfiguration of operational architecture and intraday workflows | bar: January W1 to October W3
| C - 1.2.2 | Implementation of end-to-end STP workflows | bar: January W1 to October W3
| C - 1.2.3 | Deployment of a standardized messaging framework | bar: January W1 to October W3
| C - 1.2.4 | Parameterization and alignment of operational cut-offs | bar: January W1 to October W3
| C - 1.2.5 | Enhancement of automation and exception management | bar: January W1 to October W3
| C - 1.2.6 | Enhancement of data governance and quality controls | bar: January W1 to October W3
| C - 1.2.7 | Optimization of counterparty and market connectivity | bar: January W1 to October W3
| C - 1.2.8 | Implementation of real-time monitoring and control dashboards | bar: January W1 to October W3
| C - 1.2.9 | Enhancement of automation and exception management | bar: January W1 to October W3
1.2 Clearing
A - Analysis GAP | [90 empty] | GO LIVE
| A - 1.3.1 | Analysis of operating windows | This phase should be completed during 2025
| A - 1.3.2 | Review of accounts assigned by default
| A - 1.3.3 | Evaluation of transfers and external allocations
| A - 1.3.4 | Evaluation of the acceptances of external allocations
| A - 1.3.5 | Study of netting file processing
| A - 1.3.6 | Review of derivatives expiration operations and trading near the close of the session
B - Definition of operational and technical requirements
« | B - 1.3.1 | Defining requirements associated with new schedules | bar: January W1 to April W4
« | B - 1.3.2 | Defining automatic allocation rules in clearing house operations | bar: January W1 to April W4
« | B - 1.3.3 | Establishment of automated mechanisms for the acceptance of external allocations | bar: January W1 to April W4
« | B - 1.3.4 | Definition of criteria for internal reconciliation with records of trades in the clearing house | bar: January W1 to April W4
« | B - 1.3.5 | Definition of requirements for calculating necessary balances in settlement accounts | bar: January W1 to April W4
« | B - 1.3.6 | Definition of procedures for the transfer of balances | bar: January W1 to April W4
| B - 1.3.7 | Definition of derivatives expiration operations and trading near the close of the session | bar: January W1 to April W4
C- Implementation
| C - 1.3.1 | Reconfiguration of clearing timelines, cut-offs and operating windows | bar: January W1 to October W3
| C - 1.3.2 | Automation of trade affirmation, allocation and pre-matching workflows | bar: January W1 to October W3
| C - 1.3.3 | Optimisation of netting, reconciliation and settlement instruction generation | bar: January W1 to October W3
| C - 1.3.4 | Optimisation of settlement accounts, funding and FX management | bar: January W1 to October W3
| C - 1.3.5 | Alignment of derivatives expiration and late-session trading | bar: January W1 to October W3
| C - 1.3.6 | Strengthening of settlement efficiency, fails management and reporting | bar: January W1 to October W3
1.3 Settlement
A - Analysis GAP
| A - 1.4.1 | Impact analysis of changes in operational timelines | This phase should be completed during 2025 | [87 empty] | GO LIVE
| A - 1.4.2 | Analysis to process the maximum number of instructions in real time
| A - 1.4.3 | Identification of manual or high-level operational tasks
| A - 1.4.4 | Review of data management, messaging and SSI
| A - 1.4.5 | Study of forecasting tools
| A - 1.4.6 | Analysis of partial settlement, partial release, and hold & release features
| A - 1.4.7 | Evaluation of communication flows with clients and counterparties
| A - 1.4.8 | Interoperability assessment with other markets
| A - 1.4.9 | Analysis on the use of autocollateralization and tools to increase liquidity
| A - 1.4.10 | Evaluation of allegements
B - Definition of operational and technical requirements
«2 | B - 1.4.1 | Definition of technical adjustments associated with the modifications of operational deadlines | bar: January W1 to April W4
« | B - 1.4.2 | Define requirements for the adoption of standardized communication channels and SSIs | bar: January W1 to April W4
«2 | B - 1.4.3 | Definition of requirements for the extraction and processing of data associated with partial settlement, partial release and hold & release functionalities | bar: January W1 to April W4
«2 | B - 1.4.4 | Definition of PSAFE field requirements for custodians | bar: January W1 to April W4
«2 | B - 1.4.5 | Definition of requirements for the adaptation of viable operations to RTS | bar: January W1 to April W4
« | B - 1.4.6 | Definition of operational and technical requirements to strengthen communication flows | bar: January W1 to April W4
« | B - 1.4.7 | Defining requirements for increased process automation | bar: January W1 to April W4
«2 | B - 1.4.8 | Requirements for the design or adaptation of the interface with the CCP netting system | bar: January W1 to April W4
« | B - 1.4.9 | Requirements for generating allegements | bar: January W1 to April W4
C- Implementation
| C - 1.4.1 | Reconfiguration of settlement cycles and cut-off deadlines | bar: January W1 to October W3
| C - 1.4.2 | Automation of settlement instruction processing (STP end-to-end) | bar: January W1 to October W3
| C - 1.4.3 | Enablement of partial settlement, hold & release and allegement workflows | bar: January W1 to October W3
| C - 1.4.4 | Setup of funding, intraday liquidity and autocollateralisation mechanisms | bar: January W1 to October W3
| C - 1.4.5 | Standardisation of SSI governance, messaging formats and market connectivity | bar: January W1 to October W3
| C - 1.4.6 | Automation of client and counterparty communication flows | bar: January W1 to October W3
| C - 1.4.7 | Settlement efficiency monitoring, fails management and regulatory reporting | bar: January W1 to October W3
2. CORPORATE ACTIONS
A - Analysis GAP | [90 empty] | GO LIVE
| A - 2.1.1 | Corporate Action Process Review | This phase should be completed during 2025
| A - 2.1.2 | Position Capture & Calculation Evaluation
| A - 2.1.3 | Peak Period Analysis & Resource Assessment
B - Definition of operational and technical requirements
« | B - 2.1.1 | Defining requirements for automating the corporate event cycle | bar: January W1 to April W4
| B - 2.1.2 | Requirements for the integration of structured messaging | bar: January W1 to April W4
| B - 2.1.3 | Setting up systems for anticipated calculation of rights | bar: January W1 to April W4
« | B - 2.1.4 | Definition for corporate action management | bar: January W1 to April W4
« | B - 2.1.5 | Defining requirements for automating the buyer protection instruction flow | bar: January W1 to April W4
| B - 2.1.6 | Peak Period Risk Mitigation | bar: January W1 to April W4
C- Implementation
| C - 2.1.1 | Automation and Calculation Engines | bar: January W1 to October W3
| C - 2.1.2 | Integration and Structured Messaging | bar: January W1 to October W3
| C - 2.1.3 | Buyer Protection and Market Claim | bar: January W1 to October W3
| C - 2.1.4 | Capacity and Peak Management | bar: January W1 to October W3
| C - 2.1.5 | Front-to-Back Integrations | bar: January W1 to October W3
| C - 2.1.6 | Controls and Compliance | bar: January W1 to October W3
3. TREASURY
3.1 Liquidity management
A - Analysis GAP | [90 empty] | GO LIVE
| A - 3.1.1 | Evaluation of the current liquidity forecasting model | This phase should be completed during 2025
| A - 3.1.2 | Analysis of financing mechanisms available
| A - 3.1.3 | Identification of operational restrictions for the issuance of payments
| A - 3.1.4 | Evaluation of control processes and response to deviations
| A - 3.1.5 | Analysis of repo market dependence other external sources
B - Definition of operational and technical requirements
« | B- 3.1.1 | Intraday cash forecasting requirements | bar: January W1 to April W4
« | B- 3.1.2 | Definition of buffers and liquidity cushions | bar: January W1 to April W4
« | B- 3.1.3 | Agile access to short-term financing lines | bar: January W1 to April W4
« | B- 3.1.4 | Adaptation of the processes of issuing payments on T | bar: January W1 to April W4
« | B- 3.1.5 | Update of the intraday liquidity contingency plan | bar: January W1 to April W4
« | B- 3.1.6 | Strengthen intraday liquidity forecasting | bar: January W1 to April W4
C- Implementation
| C - 3.1.1 | Strengthen intraday liquidity forecasting | bar: January W1 to October W3
| C - 3.1.2 | Calibrate and establish liquidity buffers | bar: January W1 to October W3
| C - 3.1.3 | Ensure agile access to short-term funding sources | bar: January W1 to October W3
| C - 3.1.4 | Strengthen payment issuance and prioritisation processes | bar: January W1 to October W3
| C - 3.1.5 | Implement real-time liquidity monitoring | bar: January W1 to October W3
| C - 3.1.6 | Establish controls and responses to liquidity deviations | bar: January W1 to October W3
| C - 3.1.7 | Update and test the intraday liquidity contingency plan | bar: January W1 to October W3
| C - 3.1.8 | Support systems and information flows | bar: January W1 to October W3
3.2 FX Considerations
A - Analysis GAP | [90 empty] | GO LIVE
| A-3.2.1 | Evaluation of the synchronization between the operation of securities and FX | This phase should be completed during 2025
| A-3.2.2 | FX Execution Capability Analysis at T or T+1
| A-3.2.3 | Review of dependencies with PvP systems and time restrictions
| A-3.2.4 | Evaluation of the use of bilateral settlements
| A-3.2.5 | Analysis of internal cut-offs for FX operations
B - Definition of operational and technical requirements
| B - 3.2.1 | Redesign of the FX operating flow linked to securities operations | bar: January W1 to April W4
« | B - 3.2.2 | Booking automation, confirmation and FX reconciliation | bar: January W1 to April W4
« | B - 3.2.3 | Review of the technological architecture for connection to CLS and other PvP systems | bar: January W1 to April W4
« | B - 3.2.4 | Evaluation and implementation of solutions alternatives | bar: January W1 to April W4
« | B - 3.2.5 | Cut-off adjustment and monitoring capabilities and intraday control | bar: January W1 to April W4
« | B - 3.2.6 | Strengthening of intraday monitoring and control capabilities | bar: January W1 to April W4
C- Implementation
| C - 3.2.1 | Synchronize FX and securities settlement flows | bar: January W1 to October W3
| C - 3.2.2 | Enable same-day (T0) and T+1 FX execution models | bar: January W1 to October W3
| C - 3.2.3 | Adjust and harmonize internal and external FX cut-offs | bar: January W1 to October W3
| C - 3.2.4 | Automate FX booking, confirmation, and reconciliation | bar: January W1 to October W3
| C - 3.2.5 | Upgrade connectivity and architecture for PvP and non-PvP FX | bar: January W1 to October W3
| C - 3.2.6 | Implement alternative FX execution and funding solutions | bar: January W1 to October W3
| C - 3.2.7 | Deploy integrated real-time intraday liquidity monitoring | bar: January W1 to October W3
| C - 3.2.8 | Implement robust intraday control and escalation procedures | bar: January W1 to October W3
| C - 3.2.9 | Define a cross-entity governance and communication framework | bar: January W1 to October W3
| C - 3.2.10 | Update client documentation and operational procedures | bar: January W1 to October W3
3.3 Securities financing transactions
A - Analysis GAP | [90 empty] | GO LIVE
| A-3.3.1 | Evaluation of the operating cycle of SFTs and their T+1 compatibility | This phase should be completed during 2025
| A-3.3.2 | Analysis of recall procedures and returns and degree of automation
| A-3.3.3 | Review of the collateral management model
| A-3.3.4 | Assessment of current use of intraday repos or with settlement in T
| A-3.3.5 | Diagnosis of the degree of automation in recalls and SFT flows
| A-3.3.6 | Analysis of the use of new tools for triparty and auto-borrowing operations
B - Definition of operational and technical requirements
| B - 3.3.1 | Redesign of the recall operational flow | bar: January W1 to April W4
« | B - 3.3.2 | Implementation of automated tools for the management of recalls | bar: January W1 to April W4
« | B - 3.3.3 | Optimization of the allocation process and replacement of collateral | bar: January W1 to April W4
« | B - 3.3.4 | Strengthening capacities to operate with repos intraday or with settlement in T | bar: January W1 to April W4
« | B - 3.3.5 | Assessment and integration of triparty and autoborrowing solutions | bar: January W1 to April W4
« | B - 3.3.6 | Review of cut-offs and redistribution of operational tasks | bar: January W1 to April W4
C- Implementation
| C - 3.3.1 | Align the operational cycle of SFTs with T+1 | bar: January W1 to October W3
| C - 3.3.2 | Redesign the operational flow of recalls and returns | bar: January W1 to October W3
| C - 3.3.3 | Automate recalls and end-to-end SFT operational flows | bar: January W1 to October W3
| C - 3.3.4 | Optimize and automate collateral management | bar: January W1 to October W3
| C - 3.3.5 | Strengthen intraday and T-settlement repo capabilities | bar: January W1 to October W3
| C - 3.3.6 | Integrate triparty, auto-borrowing, and auto-collateralization solutions | bar: January W1 to October W3
| C - 3.3.7 | Improve the SFT settlement model (STP, hold & release, partial) | bar: January W1 to October W3
| C - 3.3.8 | Redefine cut-offs and redistribute operational tasks | bar: January W1 to October W3
| C - 3.3.9 | Strengthen SFT data governance and quality | bar: January W1 to October W3
| C - 3.3.10 | Establish a model for governance and coordination between entities | bar: January W1 to October W3
| C - 3.3.11 | Update contractual and operational documentation | bar: January W1 to October W3
4. ASSET MANAGEMENT
A - Analysis GAP | [90 empty] | GO LIVE
| A - 4.1.1 | Development of the process taxonomy | This phase should be completed during 2025
| A - 4.1.2 | Identification of the affected taxonomy processes
| A - 4.1.3 | Evaluation of current systems
| A - 4.1.4 | Identification of the affected documentation
| A - 4.1.5 | Company reorganization
B - Definition of operational and technical requirements
« | B- 4.1.1 | Definition of requirements for sending settlement instructions in T | bar: January W1 to April W4
« | B- 4.1.2 | Definition of requirements for the selection of intermediaries | bar: January W1 to April W4
« | B- 4.1.3 | Defining requirements to increase automation in portfolio management | bar: January W1 to April W4
| B- 4.1.4 | Defining requirements for updating documentation | bar: January W1 to April W4
« | B- 4.1.5 | Defining requirements for other support areas | bar: January W1 to April W4
C- Implementation
| C - 4.1.1 | Systems, Automation and Operartions | bar: January W1 to October W3
| C - 4.1.2 | Intermediary Selection and Connectivity | bar: January W1 to October W3
| C - 4.1.3 | Portfolio and Order Management Automation | bar: January W1 to October W3
| C - 4.1.4 | Treasury, FX and Liquidity Management | bar: January W1 to October W3
| C - 4.1.5 | Corporate Actions, Securities Lending and Collateral | bar: January W1 to October W3
| C - 4.1.6 | Documentation and client communication | bar: January W1 to October W3
| C - 4.1.7 | Risk, compliance and reporting | bar: January W1 to October W3
4. DOCUMENTATION MANAGEMENT
D - External contractual documentation | [90 empty] | GO LIVE
| D - 5.1.1 | Review and update external contractual documentation
D - Internal process documentation
| D - 5.1.2 | Adapt internal process documentation
D - Staff training and customer communication
| D - 5.1.3 | Develop internal training and external communication plans
D - Impact on service level agreements (SLAs) and KPIs
| D - 5.1.4 | Review of existing affected SLAs, update and incorporate KPIs
Roadmap T+1 Spanish market
In collaboration with
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction and the functionalities it needs to develop and test
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction
TESTING
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction and the functionalities it needs to develop and test
TESTING
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction
 Task associated with a EU T+1 Industry Committee Recommendation
 Task associated with the Amendments to the RTS on Settlement Discipline
TESTING
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction and the functionalities it needs to develop and test
TESTING
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction and the functionalities it needs to develop and test
TESTING
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction and the functionalities it needs to develop and test
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction
TESTING
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction and the functionalities it needs to develop and test
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction
TESTING
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction and the functionalities it needs to develop and test
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction
TESTING
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction and the functionalities it needs to develop and test
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction
TESTING
Recommended interval for executing these tasks, which may vary depending on each entity’s situation and its level of readiness for the cycle reduction and the functionalities it needs to develop and test

## 2. Activities Detail
Area of impact | Phase | ID | Task | Related with Reference to the tasks included in the Definition of Operational and Technical Requirements | Description | HIGH-LEVEL ROADMAP TO T+1 SECURITIES SETTLEMENT IN THE EU Only the tasks within the Definition of Operational and Technical Requirements are mapped | Impacted Systems With the objective of assessing the impact arising from the implementation of ESMA’s new T+1 settlement cycle, a comprehensive review has been conducted of all systems involved across the entity’s operational value chain. The purpose of this assessment is to identify those systems that may require adjustments to ensure full regulatory compliance, maintain operational continuity, and mitigate the risks associated with the shortened settlement timeframe.
[7 empty] | Trading & Execution | Middle Office & Matching | Treasury & Payments | Risk & ALM | Data & Integration | Custody & Market Connectivity | Monitoring & Regulatory Reporting
Trade processing 1.1 TRADING | A - GAP Analysis | A - 1.1.1 | Real-time automation and integration | B - 1.1.1 | Analyse automation level and system capability for real-time API integration and automated KYC/AML, limit and collateral checks. | N/A | X | X |  |  | X |  | X
|  | A - 1.1.2 | Anticipated liquidity management | B - 1.1.2 | Review and integrate liquidity forecasting tools with Treasury and Custody systems to enable pre-matching and same-day funding. | N/A |  |  | X | X |  |  | X
|  | A - 1.1.3 | Review of procedures with the CCP | B - 1.1.3 | Review margining, netting, novation and fail workflows to align with CCP timelines and T+1 cut-offs. | N/A |  | X |  |  |  | X | X
|  | A- 1.1.4 | Study of static data management | B - 1.1.4 | Review onboarding/maintenance processes and implement automated validation/synchronisation across systems for counterparties, instruments, legal agreements and SSIs. | N/A |  |  | X |  | X | X
|  | A - 1.1.5 | Trading Regulations | B - 1.1.3 | Perform a comprehensive review to align internal practices and rules with new T+1 requirements and remediate inconsistencies. | N/A | X | [5 empty] | X
|  | A - 1.1.6 | Counterparty risk management assessment | B - 1.1.5 | Evaluate counterparty risk controls for real-time automation of KYC/AML, credit limits, exposure and compliance monitoring. | N/A | X |  |  | X |  |  | X
|  | A - 1.1.7 | Order Management Systems (OMS) Assessment | B - 1.1.6 | Upgrade OMS to support real-time regulatory validation, early settlement-instruction generation, efficient allocations, and integration with compliance/operational controls | N/A | X | X |  |  | X
|  | A - 1.1.8 | System management | B - 1.1.6 | Evaluate system readiness, automation gaps, and data dependencies impacting T+1 processing. | N/A | X | X |  |  | X |  | X
| B - Definition of operational and technical requirements | B - 1.1.1 | Definition of real-time automation and counterparty communication | N/A | Define the scope, standards, and data flow required to achieve real-time straight-through processing (STP) across trade capture and confirmation, ensuring alignment with counterparty communication protocols (FIX, ISO 20022). |  | X | X |  |  | X |  | X
|  | B - 1.1.2 | Foreign exchange (FX) management | N/A | Specify timing, rules, and internal controls for same-day FX booking, prefunding, and liquidity reservation, ensuring alignment between treasury, FX, and settlement systems. |  |  |  | X | X |  |  | X
|  | B - 1.1.3 | Cut-off review | N/A | Define operational rules and dependencies for new cut-offs, ensuring alignment across internal systems, CCPs, and market timelines for T+1. | TR-01 | X | X |  |  |  | X | X
|  | B - 1.1.4 | Settlement instruction management (SSI) | N/A | Review, document, and formalise governance and automation processes for SSI validation, ensuring ISO 15022/20022 compliance and consistency across all systems. |  |  |  | X |  | X | X
|  | B - 1.1.5 | Pre-trade monitoring and reporting | N/A | Define data and control requirements for pre-trade monitoring, including KPIs, alerts, and system integration needs. | TR-03 | X | X |  | X |  |  | X
TR-05
|  | B - 1.1.6 | Definition of shaping parameters | N/A | Establish the criteria and business logic for automatic trade shaping by nominal size, including thresholds and dependency mapping across OMS and matching systems. | TR-05 | X | X |  |  | X
| C - Implementation | C - 1.1.1 | Extend real-time STP across FO–MO–BO and enable same-day affirmation through automation, e-affirmation, and bilateral coordination with counterparties and custodians | B - 1.1.1 | Full automation of trade processing from execution through allocation and confirmation, integrating FO–MO–BO systems with intraday monitoring and automated alerting. Exception handling workflows and dashboards ensure rapid detection and resolution of discrepancies to maintain seamless post-trade operations. | N/A | X | X |  |  | X |  | X
|  |  |  | B - 1.1.6 |  | N/A
|  | C - 1.1.2 | Deploy predictive intraday liquidity and collateral models, automate prefunding and FX hedging, and enable real-time reconciliation and alerts for T+1 readiness | B - 1.1.2 | Real-time monitoring of cash and collateral positions across systems, with automated prefunding and FX coverage processes. Alerts and dashboards provide early warning of potential shortfalls, ensuring operational readiness and continuity of T+1 settlement. | N/A |  |  | X | X | X |  | X
|  | C - 1.1.3 | Centralize cut-offs, align windows across systems, update CCP processes with real-time fail/penalty handling, and simulate T+1 stress scenarios | B - 1.1.3 | Comprehensive coordination of processing windows and resolution of operational exceptions, combined with stress scenario simulations. This ensures trades are settled reliably while reducing the risk of failures and penalties across CCPs and custodians. | N/A | X | X |  |  |  | X | X
|  | C - 1.1.4 | Consolidate and normalize SSIs and critical settlement data, apply automatic validations, and maintain full audit trails with version control | B - 1.1.4 | Centralized repository of settlement instructions and critical static data, with automated validation and consistency checks. Full audit trails and version control guarantee data integrity and readiness for trade processing, minimizing settlement errors. | N/A |  | X | X |  | X | X
|  | C - 1.1.5 | Integrate T+1 pre-trade validations, update market rules and intraday limits, and deploy dashboards/KPIs to monitor allocations, confirmations, fails, and cash shortfalls | B - 1.1.5 | Assess all trades before execution with enforcement of operational thresholds and risk limits. Dashboards and alerts highlight anomalies and exceptions, enabling rapid corrective actions and ensuring compliance with internal policies and regulatory requirements. | N/A |  | X |  | X | X |  | X
|  | C - 1.1.6 | Synchronize trade execution, positions, and risk in real time, calculate intraday exposures, trigger alerts for breaches/FX shortfalls, and integrate dynamic cut-off limits | B - 1.1.2 | Implement real-time communication and monitoring with counterparties and custodians to ensure same-day affirmation visibility and control. This enables immediate detection and resolution of discrepancies, reducing operational risk and ensuring compliance with T+1 settlement timelines. | N/A |  |  | X | X | X |  | X
|  |  |  | B - 1.1.5 |  | N/A
|  | C - 1.1.7 | Connect FO–MO via bidirectional APIs and event-driven workflows, publish trade events in real time, and manage intraday exceptions with automated routing and dashboards | B - 1.1.1 | Seamless real-time flow of trade information between front and middle office, with automated detection and resolution of discrepancies. Dashboards provide full operational visibility, ensuring all exceptions are managed promptly and trades proceed without disruption. | N/A | X | X |  |  | X |  | X
|  |  |  | B - 1.1.6 |  | N/A
Trade processing 1.2 TRADE CAPTURE | A - GAP Analysis | A - 1.2.1 | Evaluation of current deadlines | B - 1.2.1 | Evaluate whether operations are assigned and confirmed within the same execution day (T), identifying the processes that are still operating at T+1. Map current allocation completion and confirmation schedules for each transaction type and counterparty and compare these timeframes with T+1 targets, identifying deviations. | N/A | X | X |  |  |  | X | X
| GAP Analysis | A - 1.2.2 | Analysis of late or erroneous allocations and confirmations | B - 1.2.2 | Identify operations that present delays or errors. Evaluate the frequency and causes of these deviations, including data discrepancies, lack of response from counterparties, field entry errors (settlement date, amount, PSET), or technological limitations.Analyze whether there are recurring patterns by asset type, customer, time zone, or operational flow. | N/A |  | X |  |  | X |  | X
| GAP Analysis | A - 1.2.3 | Analysis of the degree of automation | B - 1.2.2 | Analyze the current level of automation in assignment and confirmation processes, identifying tasks that still require manual intervention or unstructured communications. | N/A | X | X |  |  | X |  | X
| GAP Analysis | A - 1.2.4 | Review of accounts assigned by default | B - 1.2.7 | Review the current configuration of default accounts used in transaction allocation, especially daily accounts that do not have associated settlement accounts. Verify the periodic updating of these default accounts and their governance | N/A |  | X |  |  | X | X
|  | A - 1.2.5 | Analysis of standardization and quality of SSIs | B - 1.2.4 | Review whether the settlement instructions (SSIs) used in the allocation and confirmation processes are standardized and digitized. Evaluate the frequency of errors associated with incorrect or outdated SSIs, as well as the existence of mechanisms for pre-verification and ongoing maintenance of this data. | N/A |  |  | X |  | X | X
|  | A - 1.2.6 | Study of interaction with external counterparties and clients | B - 1.2.3 | Analyze operational flows that depend on third parties—including counterparties and customers—for the completion of allocations and confirmations. Identify whether these actors have the technical and organizational capacity to operate within the timeframes required by T+1, and whether there are service level agreements (SLAs) to ensure compliance. Review current customer communication mechanisms, both in onboarding processes and in daily operations with regular customers, in order to identify opportunities for improvement that will streamline the exchange of information. | N/A |  | X |  |  | X | X
|  | A - 1.2.7 | Evaluation of messaging and communication formats | B - 1.2.5 | Evaluate the use of international messaging standards (ISO 15022/20022) in the exchange of assignments and confirmations. Identify the peak times for corporate actions and analyze whether current resources (human and technological) are sufficient to manage these peaks in a T+1 environment. | N/A | X |  |  |  | X | X
|  | A - 1.2.8 | Review of the onboarding process and management of static customer data | B - 1.2.6 | Review the onboarding process for new institutional clients to ensure that all necessary information for allocation and subsequent settlement (SSIs, account details, settlement location, etc.) is collected before the first transaction. Verify the existence of controls to keep this information up to date. | N/A |  | X |  |  | X | X
|  | A - 1.2.9 | Exception control analysis and discrepancy resolution | B - 1.2.2 | Evaluate existing mechanisms to identify, escalate, and resolve discrepancies in allocations and confirmations within the same trading day. This analysis should include a review of internal reconciliation capabilities, response times and collaboration with counterparties in the event of mismatch events. | N/A |  | X |  |  | X |  | X
| B - Definition of operational and technical requirements | B - 1.2.1 | Definition of requirements regarding new deadlines | N/A | Establish the functional and technical requirements necessary to ensure that institutional allocations and confirmations are completed within the same execution day (T). Define internal cut-off times by operation type, asset class, and market and adjust exiting workflows to prioritize intra-day allocation and confirmation activities and minimize delays. Define and deploy real-time alerting mechanisms to detect threshold breaches (e.g., allocation or confirmation completion rates falling below required levels) and escalate them promptly to operational teams | MC-02 | X | X |  |  |  | X | X
|  | B - 1.2.2 | Defining requirements to increase automation of allocation and confirmation | N/A | Establish the necessary requirements to reduce manual intervention in the allocation and confirmation processes. Define requirements to automate data capture from execution systems to ensure that required trade details flow seamlessly into middle- and back-office platforms. Define automatic allocation logic based on predefined rules implementing structured messaging for exchange with counterparties | MC-05 | X | X |  |  | X |  | X
|  | B - 1.2.3 | Definition of requirements for interaction with external counterparties or third parties and clients | N/A | Establish the functional and coordination requirements necessary to ensure that processes dependent on external counterparties, third parties, and clients meet the T+1 cycle's deadlines and operational standard. Define the necessary SLA modifications to reflect the compressed timelines. Specify changes required in alerting and escalation mechanisms to promptly detect and respond to SLA breaches. Define the technical validation criteria to assess whether counterparties and clients can support business-as-usual activities under T+1 and possible outbounds. | MC-01 |  | X |  |  | X | X
|  | B - 1.2.4 | Definition of requirements for the standardization and quality of SSIs | N/A | Design a centralized management model for SSIs that ensures their standardization, integrity, and constant updating. Define technical requirements for integration of unique and validated databases. Define pre-verification controls of SSIs during trade allocation and confirmation to minimize settlement failure | MC-04 |  |  | X |  | X | X
|  | B - 1.2.5 | Definition of requirements for messaging and communication formats | N/A | Define technical specifications for using messaging standards such as ISO 15022 or ISO 20022. Define controls to ensure the availability and resilience of the messagings and communication channel . Confirm system compatibility with these formats across internal platforms. Establish a test interoperability with third-party systems (brokers, custodians, CCPs, and other intermediaries) | MC-01 | X |  |  |  | X | X
|  | B - 1.2.6 | Defining requirements for onboarding and managing static customer data | N/A | Establish a structured process for registering new institutional clients that ensures the availability of all necessary data for allocation and subsequent settlement. Define controls over account and settlement location data. Define mechanisms to keep client and account databases continuously up-to-date, including version control and automated alerts for incomplete or outdated records. | MC-01 |  | X |  |  | X | X
|  | B - 1.2.7 | Definition of requirements for the PSET | N/A | Define operational and functional requirements that require the capture and transmission of PSET data at the time of trade allocation. Integrate PSET information into post-trade workflows so that it is available to all internal and external systems involved in the settlement process. Establish data quality controls and reconciliation procedures to ensure that PSET information is accurate and consistent across the full trade lifecycle. | MC-03 |  |  | X |  | X | X
| C - Implementation | C - 1.2.1 | Reconfiguration of operational architecture and intraday workflows | B - 1.2.1 | Define the scope, standards, and data flow required to achieve real-time straight-through processing (STP) across trade capture and confirmation, ensuring alignment with counterparty communication protocols (FIX, ISO 20022). | N/A | X | X |  |  | X |  | X
|  | C - 1.2.2 | Implementation of end-to-end STP workflows | B - 1.2.2 | Deploy real-time straight-through processing (STP) from trade capture to settlement, automating allocation, confirmation, and validation to eliminate manual interventions and late matching. | N/A | X | X |  |  | X |  | X
|  | C - 1.2.3 | Deployment of a standardized messaging framework | B - 1.2.5 | Adopt a unified messaging structure based on FIX and ISO 20022 standards to ensure full interoperability between internal systems and external counterparties, improving traceability and data consistency. | N/A | X |  |  |  | X | X
|  | C - 1.2.4 | Parameterization and alignment of operational cut-offs | B - 1.2.1 | Configure and synchronize internal and market cut-offs across all systems and asset classes, incorporating automated alerts and monitoring tools to ensure compliance with T+1 timelines. | N/A | X | X |  |  |  | X | X
|  | C - 1.2.5 | Enhancement of automation and exception management | B - 1.2.2 | Strengthen automation across allocation, confirmation, and reconciliation processes, supported by a centralized exception management tool for real-time incident detection, routing, and resolution. | N/A | X | X |  |  | X |  | X
|  | C - 1.2.6 | Enhancement of data governance and quality controls | B - 1.2.4 | Consolidate a master repository for critical reference data (SSIs, accounts, clients, PSETs) with automatic validation, coherence checks, and audit trails to ensure data reliability throughout the trade lifecycle. | N/A |  | X | X |  | X | X
|  |  |  | B - 1.2.6 |  | N/A
|  | C - 1.2.7 | Optimization of counterparty and market connectivity | B - 1.2.3 | Upgrade connectivity with counterparties, custodians, CSDs, and CCPs using standardized APIs and interoperability testing to enable secure and stable real-time communication. | N/A | X |  |  |  | X | X
|  | C - 1.2.8 | Implementation of real-time monitoring and control dashboards | B - 1.2.7 | Deploy integrated dashboards to provide end-to-end visibility of trade progress, automation rates, and cut-off adherence, with metrics and alerts for operational performance and incident tracking. | N/A |  |  |  | X | X |  | X
|  | C - 1.2.9 | Strengthening of compliance, security, and traceability controls |  | Reinforce system security and data traceability by implementing enhanced access controls, segregation of duties, and audit logging, ensuring compliance with ESMA, CSDR, and internal policies. | N/A |  |  |  | X | X | X | X
Trade processing 1.3 CLEARING | A - GAP Analysis | A - 1.3.1 | Analysis of operating windows | B - 1.3.1 | Analyze current operating hours and the entity's ability to comply with the new cutoff times. This includes reviewing the availability of staff, technical support, technological resources, and the ability to execute processes. Assess whether there are any dependencies on third parties (e.g. custodians, trading platforms, clients) that could limit operations. | N/A | X | X |  |  |  | X | X
|  | A - 1.3.2 | Review of accounts assigned by default | B - 1.3.5 | Review the current configuration of default accounts used in transaction allocation, especially day-to-day accounts that do not have associated settlement accounts. Verify the periodic updating of these default accounts and their governance. | N/A |  |  | X |  | X | X
|  | A - 1.3.3 | Evaluation of transfers and external allocations | B - 1.3.2 | Evaluate the current time required to process and complete transfers and allocations from the moment of execution to final acceptance. The analysis should identify critical operational points related to manual tasks and response times. Consideration should be given to implementing automation and using structured procedures that allow these processes to be completed within the same trading day. Review the possibility of automating the allocations to achieve automation in the process. | N/A |  | X |  |  | X | X
|  |  |  | B - 1.3.3 |  | N/A
|  | A - 1.3.4 | Evaluation of the acceptances of external allocations | B - 1.3.3 | Evaluate the current time required to accept these assignments and compare them with the deadlines imposed by the T+1 cycle. Operational limitations or manual processes that may prevent or delay acceptance should be identified. The analysis should also include the systems' ability to process operations in real or near real time. | N/A |  | X |  |  |  | X | X
|  | A - 1.3.5 | Study of netting file processing | B - 1.3.4 | Analyze the entity's ability to execute position reconciliation processes more quickly and frequently. This includes reviewing systems, tasks to be performed, and operational flows associated with validating netted positions, margins, and balances with the CCP. Necessary improvements must be identified to carry out these processes within shorter time windows. | N/A |  | X |  |  | X | X
|  | A - 1.3.6 | Review of derivatives expiration operations and trading near the close of the session | B - 1.3.7 | Analyze the current operational flow of allocations in derivative expiration dates and trades near the close of the session. Identify possible automation measures in the allocation of these operations and action plans to achieve the required cut-off times. | N/A | X | X |  |  |  | X | X
| B - Definition of operational and technical requirements | B - 1.3.1 | Defining requirements associated with new schedules | N/A | Define and establish the required operating schedules . Determine the maximum timeframes for executing each process. Based on these schedules, all functional and operational requirements necessary to meet them must be specified, including system adaptations, task automation, staff shift adjustments, and coordination with third parties. | CL-01 CL-02 | X | X |  |  |  | X | X
|  | B - 1.3.2 | Defining automatic allocation rules in clearing house operations | N/A | Define clear business rules for the automatic allocation of trades assignment based on the information available in the order. Establish validation checks to ensure correct assignment of trades according to these rules. Validations to ensure correct assignment. Note that all transactions without an informed account and without automatic allocation rules are recorded in the member's default account. Define the operational criteria, technical specifications, and control requirements for the use of parameterization modules. Enable the use of parameterization modules to allow members to automate allocations by redirecting trades to a designated account, or assigning trades directly to another member (external allocation). Define a scheme for the periodic review and validation of allocation configurations. | CL-02 |  | X |  |  | X | X
|  | B - 1.3.3 | Establishment of automated mechanisms for the acceptance of external allocations | N/A | Establish mechanisms to automatically accept or reject external allocations using structured references, reducing manual intervention and mitigating the risk of delayed or failed acceptance. Define cut-off time windows for the receipt and acceptance of external allocation instructions. Configure automated alerts to notify stakeholders of pending or rejected external allocations, enabling timely follow-up and resolution | CL-02 |  | X |  |  |  | X | X
|  | B - 1.3.4 | Definition of criteria for internal reconciliation with records of trades in the clearing house | N/A | Define functionalities that allow the automatic cross-referencing of netting file information with internal records of trades executed during the day. This reconciliation must ensure that there are no discrepancies between the amounts netted by the clearing house and those recorded in the clearing member's systems. | CL-02 |  | X |  |  | X | X | X
|  | B - 1.3.5 | Definition of requirements for calculating necessary balances in settlement accounts | N/A | Establish automatic rules to validate, based on the netting file received by the CCP, the cash and securities balances required for each settlement account. Define systems alerts if discrepancies are detected with available balances or if potential defaults are anticipated. This validation must be performed immediately upon receipt of the file to allow for a reaction time before the settlement window. | CL-02 |  | X |  |  | X | X
|  | B - 1.3.6 | Definition of procedures for the transfer of balances | N/A | Define procedures to promptly forward netting information to institutional clients and internal departments responsible for safeguarding assets or managing liquidity | CL-02 |  |  | X |  |  | X
|  | B - 1.3.7 | Definition of derivatives expiration operations and trading near the close of the session | N/A | Define automation measures in the allocation of derivative expiration dates and trades near the close of the session operations and action plans to achieve the required cut-off times. |  | X | X |  |  |  | X | X
| C - Implementation | C - 1.3.1 | Reconfiguration of clearing timelines, cut-offs and operating windows | B - 1.3.1 | Comprehensive adjustment of post-trade operating cycles to meet T+1 deadlines. This includes reparameterising operating windows, defining new internal cut-offs and SLAs, and coordinating across time zones with custodians, CSDs and CCPs to ensure affirmation and acceptance of trades within T+0. | N/A | X | X |  |  |  | X | X
|  | C - 1.3.2 | Automation of trade affirmation, allocation and pre-matching workflows | B - 1.3.2 | Deployment of fully automated processes for same-day allocation, affirmation and pre-matching. Covers automated internal and external allocation rules, validation of critical data (including SSI/SSSA), and front-to-back integration to eliminate manual intervention and enable full STP. | N/A |  | X |  |  | X | X | X
|  |  |  | B - 1.3.3 |  | N/A
|  | C - 1.3.3 | Optimisation of netting, reconciliation and settlement instruction generation | B - 1.3.4 | Strengthening of netting and reconciliation across internal systems, CCPs and custodians, resolving discrepancies intraday. Includes automated early generation of settlement instructions, reinstruction capabilities and support for partial settlement to minimise fails and delays. | N/A |  | X |  |  | X | X
|  | C - 1.3.4 | Optimisation of settlement accounts, funding and FX management | B - 1.3.5 | Ensuring same-day liquidity and currency availability to meet T+1 settlement requirements. Includes prefunding processes, FX booking/hedging, alignment with treasury systems and intraday monitoring of cash and collateral positions. | N/A |  |  | X |  | X | X | X
|  |  |  | B - 1.3.6 |  | N/A
|  | C - 1.3.5 | Alignment of derivatives expiration and late-session trading | B - 1.3.7 | Adjustment and automation of exercise/assignment processes for derivatives and trades executed near market close. Ensures timely creation of underlying settlement instructions, operational prioritisation at end of day and contingency mechanisms to reduce operational risk. | N/A | X | X |  |  |  | X | X
|  | C - 1.3.6 | Strengthening of settlement efficiency, fails management and reporting | B - 1.3.1 | Enhancement of settlement efficiency controls in line with regulatory standards. Involves intraday monitoring of fails, automated retries and reinstructions, definition of KPI dashboards, and generation of regulatory and internal reports to ensure transparency and continuous improvement. | N/A |  | X |  |  |  | X | X
|  |  |  | B - 1.3.4 |  | N/A
|  |  |  | B - 1.3.5 |  | N/A
Trade processing 1.4 SETTLEMENT | A - GAP Analysis | A - 1.4.1 | Impact analysis of changes in operational timelines | B - 1.4.1 | Identify how the shortened cycle affects instruction matching, settlement finality, and exception management. Assess dependencies between internal systems and external market infrastructures, evaluating whether current processes, cut-off times, and automated workflows ensure timely settlement under the T+1 | N/A | X | X |  |  | X | X | X
| GAP Analysis | A - 1.4.2 | Analysis to process the maximum number of instructions in real time | B - 1.4.7 | Evaluate which transactions currently managed during the RTS settlement cycle can be brought forward to the NTS cycle. The objective is to identify opportunities for improvement in the preparation and transmission of instructions, reducing the operational burden on the same day of settlement and anticipating the positive effects of early settlement, which facilitates resources for further settlement. | N/A |  | X |  |  | X | X | X
| GAP Analysis | A - 1.4.3 | Identification of manual or high-level operational tasks | B - 1.4.7 | Identify manual operational tasks by assessing their optimization potential through automation, standardized templates, internal solutions, or new tools. The analysis should prioritize critical processes for T+1, such as instruction management, reconciliations, and monitoring exceptions or settlement failures. | N/A |  | X |  |  | X |  | X
|  | A - 1.4.4 | Review of data management, messaging and SSI | B - 1.4.2 | Review current data extraction processes, the use of standardized messaging (ISO 15022/20022), and SSI management to identify gaps and improvement needs. . The analysis must ensure that the necessary data is available in real time and correctly structured to allow for the automatic generation and validation of instructions. Review position reporting systems (Statement of Holding) to include the PSAF field. | N/A |  |  | X |  | X | X | X
|  | A - 1.4.5 | Study of forecasting tools | B - 1.4.5 | Evaluate whether adequate cash flow and position forecasting capabilities are available and determine whether implementation or adaptation of forecasting tools is necessary.This analysis should take into account the reduction in time available for covering cash needs and making financing decisions. | N/A |  |  | X | X | X |  | X
|  | A - 1.4.6 | Analysis of partial settlement, partial release, and hold & release features | B - 1.4.3 | Conduct an internal review to check whether the entity can operate efficiently with features such as partial settlement, partial release and hold & release, and analyze their impact on daily operations and their clients, taking into account the different types of clients | N/A |  | X |  |  | X | X
|  | A - 1.4.7 | Evaluation of communication flows with clients and counterparties | B - 1.4.6 | Analyze communication flows with clients and counterparties to ensure a complete and timely exchange of information, enabling compliance with the operational deadlines required by T+1. This analysis should focus on identifying potential deficiencies in existing channels, as well as gaps in the flow of information, understood as points where data is transmitted incompletely, incorrectly, or with delays. | N/A |  |  |  |  | X | X | X
|  | A - 1.4.8 | Interoperability assessment with other markets | B - 1.4.8 | Evaluate the operational impact of interoperability between national and international infrastructures, identifying the necessary changes in internal processes and systems to adapt to different schedules, settlement rules, or instruction formats | N/A |  |  |  |  | X | X
|  | A - 1.4.9 | Analysis on the use of autocollateralization and tools to increase liquidity | B - 1.4.5 | Determine whether the entity can use autocollateralization or other intraday funding techniques to reduce settlement failures due to insufficient funds | N/A |  |  | X | X |  | X
|  |  |  | B - 1.4.6 |  | N/A
|  | A - 1.4.10 | Evaluation of allegements | B - 1.4.9 | Evaluate whether the current system allows for automatic identification and reporting of allegements in real time, and detect gaps in the visibility of unmatched instructions for participants. | N/A |  | X |  |  |  | X | X
| B - Definition of operational and technical requirements | B - 1.4.1 | Definition of technical adjustments associated with the modifications of operational deadlines | N/A | Establish an internal operating calendar and define cut-off times for processing instructions. This design should be aligned with market cutoff times, include windows for validation and error correction, and provide for coordination with custodians, CSDs and CCPs. | ST-02 | X | X |  |  | X | X | X
|  | B - 1.4.2 | Define requirements for the adoption of standardized communication channels and SSIs | N/A | Establish the functional and technical requirements necessary to implement standardized communication channels and the adoption or updating of SSIs. This includes impact analysis on front-to-back systems, automated validations, SSI database maintenance, and adaptation of reconciliation and monitoring processes. | ST-01.2 |  |  | X |  | X | X
| Definition of operational and technical requirements | B - 1.4.3 | Definition of requirements for the extraction and processing of data associated with partial settlement, partial release and hold & release functionalities | N/A | Design the specifications necessary to capture, process, and exploit the data that enables these functionalities. This involves defining how they are enabled, in what scenarios they are used (e.g., by asset type, trade amount), how decisions are notified to the market, and how exceptions or held instructions are handled. | ST-03.1 ST-03.2 ST-03.5 ST-03.6 ST-03.7 |  | X |  |  | X | X
| Definition of operational and technical requirements | B - 1.4.4 | Definition of PSAFE field requirements for custodians | N/A | For custodian entities, specify the requirements for capturing, storing, validating, and transmitting the PSAF field in SWIFT messages. | ST-01.4 | [5 empty] | X | X
| Definition of operational and technical requirements | B - 1.4.5 | Definition of requirements for the adaptation of viable operations to RTS | N/A | Define and document the functional, technical, and operational requirements necessary to adapt eligible transactions for settlement during the RTS cycle. | ST-01.1 |  |  | X | X | X
|  | B - 1.4.6 | Definition of operational and technical requirements to strengthen communication flows | N/A | Establish the operational and technical requirements necessary to improve communication flows with counterparties and clients, with the aim of ensuring the availability and quality of information. Furthermore, define specific procedures and mechanisms to quickly detect and resolve situations involving missing, erroneous, or inconsistent information, thereby minimizing the risk of settlement errors. | ST-01.2 ST-0.2 |  |  | X |  | X | X
|  | B - 1.4.7 | Defining requirements for increased process automation | N/A | Develop operational and technological requirements to improve STP rates in critical activities such as instruction generation, confirmations, reconciliations, alert management, and exception tracking, focusing on reducing manual intervention. | ST-01.2 ST-03.13 |  | X |  |  | X | X | X
|  | B - 1.4.8 | Requirements for the design or adaptation of the interface with the CCP netting system | N/A | Design or adapt the interface to the CCP netting system, prioritizing STP automation and ensuring that netted instruction files are properly validated before being sent to the NTS | ST-02 |  |  |  |  | X | X
| Definition of operational and technical requirements | B - 1.4.9 | Requirements for generating allegements | N/A | Define functional requirements that ensure the system automatically detects unmatched instructions (allegements) in T2S and generates real-time notifications to internal and external users (brokers, custodians, etc.). | ST-03.8 ST-03.8a |  | X |  |  |  | X | X
| C - Implementation | C - 1.4.1 | Reconfiguration of settlement cycles and cut-off deadlines | B - 1.4.1 | Adjust internal and external settlement cycles to support T+1. This includes redefining cut-offs with CSDs and custodians, updating internal SLAs across FO–MO–BO, aligning deadlines across time zones, and enabling affirmation and matching within T+0 instead of overnight. | N/A | X | X |  |  | X | X | X
|  | C - 1.4.2 | Automation of settlement instruction processing (STP end-to-end) | B - 1.4.7 | Implement end-to-end STP workflows to generate, validate, and transmit settlement instructions in real time. Replace manual sequencing with automated enrichment (SSI, PSET, CSD account), reduce batch processing, and ensure STP from booking to confirmation and transmission to CSD/CCP. | N/A |  | X |  |  | X | X | X
|  | C - 1.4.3 | Enablement of partial settlement, hold & release and allegement workflows | B - 1.4.3 | Enable systems to support partial settlement, auto-release, cancellation, and allegement processing. Instructions must update instantly based on counterparty feedback, with automated alerts, exception management, and re-submission before market cut-offs. | N/A |  | X |  |  | X | X | X
|  |  |  | B - 1.4.9 |  | N/A
|  | C - 1.4.4 | Setup of funding, intraday liquidity and autocollateralisation mechanisms | B - 1.4.5 | Develop intraday liquidity forecasting for settlement accounts, ensure prefunding availability in multiple currencies, and activate autocollateralisation tools with custodians or CCPs. Treasury must receive real-time updates on cash needs, collateral movements and expected settlement flows. | N/A |  |  | X | X |  | X
|  |  |  | B - 1.4.6 |  | N/A
|  | C - 1.4.5 | Standardisation of SSI governance, messaging formats and market connectivity | B - 1.4.2 | Migrate settlement messaging to ISO 20022/15022 structured formats, harmonise SSI storage in a golden source, and ensure interoperability with CSDs, custodians, CCPs and counterparties. Includes MT5xx migration, PSET validation and LEI/BIC checks. | N/A |  |  | X |  | X | X
|  | C - 1.4.6 | Automation of client and counterparty communication flows | B - 1.4.6 | Digitalise and automate communication with brokers, clients, custodians and counterparties. Implement structured workflows for settlement status updates, fails notifications, buyer protection and hold/release messaging to reduce email/manual communication. | N/A |  |  |  |  | X | X | X
|  | C - 1.4.7 | Settlement efficiency monitoring, fails management and regulatory reporting | B - 1.4.4 | Deploy dashboards to monitor settlement KPIs (settlement rate, fails, allegements), automate penalty (CSDR) and re-instruction workflows, and integrate regulatory reporting such as RTS, PSAF, CSDR settlement discipline and SRD II. | N/A |  |  |  |  | X | X | X
|  |  |  | B - 1.4.8 |  | N/A
2. CORPORATE ACTIONS | A - GAP Analysis | A - 2.1.1 | Corporate Action Process Review | B - 2.2.1 B - 2.2.2 B - 2.2.4 B - 2.2.5 | Analyze current operational processes for corporate action management, including rights identification, election validation, instruction execution, action closure, and claims management. Evaluate the impact of the new calendar and new corporate action operations on internal processes. This review should incorporate an assessment of the degree of automation, processing times, communication channels used (structured messaging, internal files, platforms), and manual intervention | N/A | X | X | X |  | X | X
|  | A - 2.1.2 | Position Capture & Calculation Evaluation | B - 2.2.3 | Review how systems capture and process positions used to determine rights in corporate actions. Determine if processes need to be brought forward or if the configuration of data sources (e.g., CSDs, custodians) needs to be improved to make the information available on T+0, considering the impact of the change in ex-date and record date | N/A |  | X | X |  | X | X | X
|  | A - 2.1.3 | Peak Period Analysis & Resource Assessment | B - 2.2.6 | Identify the peak times for corporate actions and analyze whether current resources (human and technological) are sufficient to manage these peaks in a T+1 environment. This review should include staffing schedules, workloads, real-time monitoring systems, and the availability of technical support outside of standard business hours | N/A |  | X |  |  | X | X
| B - Definition of operational and technical requirements | B - 2.1.1 | Defining requirements for automating the corporate event cycle | N/A | Establish the functional requirements necessary to automate the processing of corporate actions from receipt of the notice to final execution. This includes parameterizing automatic rules for interpreting corporate actions, recognizing holders, automating buyer protection processing, and managing claims. | CE-01 CE-02 | X | X | X |  | X | X
|  | B - 2.1.2 | Requirements for the integration of structured messaging | N/A | Define the technical developments for sending and receiving corporate action messages, market claim instructions, and Buyer Protection instructions in structured formats compatible with ISO 20022 standards, according to the standards defined in SCoRE. Define and configure translation and validation tools required to ensure the accurate processing of corporate action data and event notifications across systems. Specify interfaces and data mapping rules to standardize event information received from different sources (CSDs, custodians, market infrastructures). |  |  | X |  |  | X | X | X
|  | B - 2.1.3 | Setting up systems for anticipated calculation of rights | N/A | Specify the requirements for advancing calculations of rights associated with corporate actions (dividends, subscriptions, splits, etc.) based on positions recorded in T-1 (at the close of the record-date / Market Deadline) |  |  | X | X |  | X | X
|  | B - 2.1.4 | Definition for corporate action management | N/A | Adapt systems to properly process actions whose key dates have been shortened under T+1. Same day as the ex-date and the record date in distributions, one business day advance of the last trade date in mandatory reorganizations and one business day between Guaranteed Participation Date and Buyer Protection Deadline, and two business days until the Market Deadline. Define the reconfiguration system parameters, adjustment of event generation logic, and update customer communication schedules to reflect the compressed timeline. | CE-01 CE-02 |  | X |  |  | X | X | X
|  | B - 2.1.5 | Defining requirements for automating the buyer protection instruction flow | N/A | Define functional developments that enable the automation of the reception, validation, processing, and confirmation of buyer protection instructions, from the customer to the CSD | CE-01 CE-02 | X | X | X |  | X | X
|  | B - 2.1.6 | Peak Period Risk Mitigation | N/A | Establish reinforcement and redistribution mechanisms to mitigate the risk of operational errors in critical corporate action processes, particularly during periods of high activity (e.g., corporate action peaks, quarter-end). |  |  | X | X |  | X | X | X
| C -Implementation | C - 2.1.1 | Automation and Calculation Engines | B - 2.2.1 | Reduce operational risk and processing time in a T+1 environment by automating entitlement and position calculation. | N/A | X | X | X |  | X | X
B - 2.2.3
B - 2.2.4
|  | C - 2.1.2 | Integration and Structured Messaging | B - 2.2.2 | Ensure interoperability and full traceability through the adoption of market standards. | N/A |  | X |  |  | X | X | X
B - 2.2.4
|  | C - 2.1.3 | Buyer Protection and Market Claim | B - 2.2.1 | Automate instruction flows and claims handling in line with new T+1 deadlines. | N/A | X | X | X |  | X | X | X
B - 2.2.5
|  | C - 2.1.4 | Capacity and Peak Management | B - 2.2.1 | Ensure operational stability during high-volume or peak periods. | N/A |  | X | X |  | X | X | X
B - 2.2.6
|  | C - 2.1.5 | Front-to-Back Integrations |  | Improve visibility and data consistency across the full Corporate Actions lifecycle, from front office to post-trade. | N/A | X | X | X | X | X | X
|  | C - 2.1.6 | Controls and Compliance | B - 2.2.4 | Ensure traceability, SRD II compliance, and effective monitoring of T+1 regulatory deadlines. | N/A |  | X | X |  | X | X | X
Treasury 3.1 LIQUIDITY MANAGEMENT | A - GAP Analysis | A - 3.1.1 | Evaluation of the current liquidity forecasting model | B- 3.1.1 | Analyze cash forecasting (horizon, automation, frequency, granularity). | N/A |  |  | X | X | X |  | X
|  | A - 3.1.2 | Analysis of financing mechanisms available | B- 3.1.2 B- 3.1.3 | Review immediate liquidity sources. | N/A |  |  | X | X | X | X
|  | A - 3.1.3 | Identification of operational restrictions for the issuance of payments | B- 3.1.4 | Assess same-day (T) payment capability and related constraints. | N/A |  |  | X |  | X | X | X
|  | A - 3.1.4 | Evaluation of control processes and response to deviations | B- 3.1.5 | Review operational controls and escalation efficiency. | N/A |  |  | X | X | X |  | X
|  | A - 3.1.5 | Analysis of repo market dependence other external sources | B- 3.1.6 | Evaluate repo exposure and collateral mobilization capacity. | N/A |  |  | X | X | X | X
| B - Definition of operational and technical requirements | B- 3.1.1 | Intraday cash forecasting requirements | N/A | Define requirements for real-time liquidity forecasting. | TR-03 |  |  | X | X | X |  | X
|  | B- 3.1.2 | Definition of buffers and liquidity cushions | N/A | Set minimum intraday liquidity buffers. | TR-03 |  |  | X | X |  |  | X
|  | B- 3.1.3 | Agile access to short-term financing lines | N/A | Ensure access to overnight and intraday funding. | TR-03 ST-03.14 |  |  | X | X | X | X
|  | B- 3.1.4 | Adaptation of the processes of issuing payments on T | N/A | Automate same-day payment generation and validation. | TR-03 |  |  | X |  | X | X | X
|  | B- 3.1.5 | Implementation of monitoring tools in real time and updating contingency plans | N/A | Develop dashboards for real-time liquidity and key events. | TR-03 ST-03.10 |  |  | X | X | X |  | X
|  | B- 3.1.6 | Update of the intraday liquidity contingency plan | N/A | Define responses and escalation for payment or funding issues. | TR-03 |  |  | X | X |  | X | X
| C -Implementation | C - 3.1.1 | Strengthen intraday liquidity forecasting | B- 3.1.1 | Develop and integrate a near real-time liquidity forecasting model that consolidates expected cash flows from settlements, margin calls, corporate actions and operational payments/receipts. | N/A |  |  | X | X | X |  | X
|  | C - 3.1.2 | Calibrate and establish liquidity buffers | B- 3.1.2 | Define and apply structural and dynamic minimum liquidity buffers per currency, account and custodian, based on statistical analysis of historical peaks and stress scenarios. | N/A |  |  | X | X |  |  | X
|  | C - 3.1.3 | Ensure agile access to short-term funding sources | B- 3.1.3 | Guarantee immediate availability of liquidity to cover timing gaps between inflows and outflows on trade date, by reviewing and securing intraday credit lines, bilateral or tri-party repo agreements, and correspondent/bank or central bank facilities. | N/A |  |  | X | X | X | X
|  | C - 3.1.4 | Strengthen payment issuance and prioritisation processes | B- 3.1.4 | Redesign payment queues based on criticality (securities settlement, margin calls, internal transfers, etc.), ensuring full STP processing and compliance with cut-offs. Implement automatic prioritisation and validation rules in payment systems (T2, T2S, SWIFT) to avoid settlement failures caused by operational delays or late approvals. | N/A |  |  | X |  | X | X | X
|  | C - 3.1.5 | Implement real-time liquidity monitoring | B- 3.1.5 | Develop or enhance dashboards that display current and projected cash positions, buffer usage, credit line consumption and status of critical payments. Include automatic alerts for deviations, liquidity shortfalls or operational incidents. | N/A |  |  | X | X | X |  | X
|  | C - 3.1.6 | Establish controls and responses to liquidity deviations | B- 3.1.2 B- 3.1.5 | Ensure operational discipline and full traceability by setting a daily control framework with checkpoints (start of day, midday, end of day), forecast vs actual reconciliations, and predefined response protocols for significant variances. | N/A |  |  | X | X | X |  | X
|  | C - 3.1.7 | Update and test the intraday liquidity contingency plan | B- 3.1.6 | Update the contingency plan to include T+1-specific scenarios (settlement fails, custodian delays, system outages, etc.) and define procedures, roles, contact points and response times by event type. | N/A |  |  | X | X |  | X | X
|  | C - 3.1.8 | Support systems and information flows | B- 3.1.1 B- 3.1.4 B- 3.1.5 | Adapt interfaces, systems and data flows to enable intraday cash forecasting, real-time monitoring, automated payment processing and liquidity contingency procedures. | N/A |  |  | X |  | X | X | X
Treasury 3.2 FX CONSIDERATIONS | A - GAP Analysis | A-3.2.1 | Evaluation of the synchronization between the operation of securities and FX | B - 3.2.1 | Check FX–securities synchronization under T+1 to avoid settlement gaps. | N/A | X | X | X |  | X | X
|  | A-3.2.2 | FX Execution Capability Analysis at T or T+1 | B - 3.2.2 | Assess FX execution capability on T/T+1 and system readiness. | N/A | X |  | X |  | X |  | X
|  | A-3.2.3 | Review of dependencies with PvP systems and time restrictions | B - 3.2.3 | Review PvP (e.g., CLS) compatibility with T+1 timelines. | N/A |  |  | X |  | X | X
|  | A-3.2.4 | Evaluation of the use of bilateral settlements | B - 3.2.4 | Evaluate bilateral settlement reliance and related risk controls. | N/A | X |  | X |  | X | X
|  | A-3.2.5 | Analysis of internal cut-offs for FX operations | B - 3.2.5 B - 3.2.6 | Reassess internal FX cut-offs to align with T+1 settlement. | N/A | X |  | X |  | X
| B - Definition of operational and technical requirements | B - 3.2.1 | Redesign of the FX operating flow linked to securities operations | N/A | Redesign FX workflow to ensure synchronized execution and settlement with securities under T+1, possibly using auto-hedging (autoforex). |  | X | X | X |  | X | X
|  | B - 3.2.2 | Booking automation, confirmation and FX reconciliation | N/A | Automate FX booking, confirmation, and reconciliation to meet T+1 deadlines and enable real-time processing. | FX-01 | X |  | X |  | X |  | X
|  | B - 3.2.3 | Review of the technological architecture for connection to CLS and other PvP systems | N/A | Review tech architecture to ensure timely connection with CLS and other PvP systems, supporting automated instructions across currencies and time zones. | FX-04 | X | X | X |  | X
|  | B - 3.2.4 | Evaluation and implementation of solutions alternatives | N/A | Assess and implement alternative solutions (prefunding, autoforex, bilateral FX) with clear usage conditions, risks, and controls. |  |  |  | X |  | X | X
|  | B - 3.2.5 | Cut-off adjustment and monitoring capabilities and intraday control | N/A | Adjust internal cut-offs and redesign SLAs between teams to meet T+1 timelines and enhance coordination. | FX-02 |  |  | X |  | X |  | X
|  | B - 3.2.6 | Strengthening of intraday monitoring and control capabilities | N/A | Strengthen intraday monitoring tools and alerts to track FX execution and settlement, especially for off-hours or illiquid currencies. | FX-03 |  |  | X |  | X |  | X
| C -Implementation | C - 3.2.1 | Synchronize FX and securities settlement flows | B - 3.2.1 | Align FX and securities settlement workflows through STP processes that connect trade execution, confirmation, and funding to ensure coherence and compliance under T+1. | N/A |  | X | X | X | X
|  | C - 3.2.2 | Enable same-day (T0) and T+1 FX execution models | B - 3.2.2 | Develop operational capability to execute and confirm FX trades on T or T+1, depending on currency and time zone, ensuring compatibility with shortened settlement timelines. | N/A | X |  | X | X | X
|  | C - 3.2.3 | Adjust and harmonize internal and external FX cut-offs | B - 3.2.5 | Define and coordinate internal and external FX cut-off times (CLS, custodians, CSDs, RTGS) through a consolidated calendar that guarantees timely funding and hedging. | N/A | X |  | X | X | X |  | X
|  | C - 3.2.4 | Automate FX booking, confirmation, and reconciliation | B - 3.2.2 | Implement full automation of FX capture, confirmation, and reconciliation, leveraging clean static data and standardized SSIs to minimize manual intervention and operational risk. | N/A |  | X | X | X | X
|  | C - 3.2.5 | Upgrade connectivity and architecture for PvP and non-PvP FX | B - 3.2.3 | Modernize connectivity to PvP systems (CLS and equivalents) and establish controlled frameworks for bilateral/non-PvP settlements to mitigate settlement risk. | N/A |  |  | X | X | X
|  | C - 3.2.6 | Implement alternative FX execution and funding solutions | B - 3.2.4 | Adopt alternative funding and execution models (prefunding, local accounts, netting, extended windows) for currencies or markets with time or infrastructure constraints. | N/A |  |  | X | X | X | X
|  | C - 3.2.7 | Deploy integrated real-time intraday liquidity monitoring | B - 3.2.6 | Implement real-time monitoring tools that consolidate cash positions, FX movements, and liquidity needs across currencies and systems to support T+1 funding. | N/A |  |  | X | X | X | X | X
|  | C - 3.2.8 | Implement robust intraday control and escalation procedures | B - 3.2.6 | Define control mechanisms, prioritization rules, and escalation workflows to manage FX and securities settlement delays or failures within the T+1 timeline. | N/A |  | X | X | X | X |  | X
|  | C - 3.2.9 | Define a cross-entity governance and communication framework | B - 3.2.1 B - 3.2.3 | Establish governance structures and communication protocols between dealers, custodians, CSDs, CCPs, and buy-side entities, including roles, SLAs, and daily coordination channels. | N/A |  | X | X |  | X
|  | C - 3.2.10 | Update client documentation and operational procedures | B - 3.2.4 B - 3.2.5 | Update contractual documentation, operational manuals, and client communications to reflect new FX cut-offs, settlement methods, and responsibilities under T+1. | N/A |  | X | X |  | X |  | X
Treasury 3.3 SECURITIES FINANCING TRANSACTIONS | A - GAP Analysis | A-3.3.1 | Evaluation of the operating cycle of SFTs and their T+1 compatibility | B - 3.3.1 | Assess SFT operational cycle (repos, securities lending) and its compatibility with T+1, focusing on settlement timing and collateral release capabilities. | N/A | X | X |  |  | X | X | X
|  | A-3.3.2 | Analysis of recall procedures and returns and degree of automation | B - 3.3.2 | Evaluate recall and return procedures, ensuring same-day or early execution, automation, and compliance with regulatory timelines. | N/A |  | X |  |  | X |  | X
|  | A-3.3.3 | Review of the collateral management model | B - 3.3.3 | Review collateral management model to ensure timely allocation, substitution, and monitoring aligned with T+1 and margin call requirements. | N/A |  | X | X | X | X | X
|  | A-3.3.4 | Assessment of current use of intraday repos or with settlement in T | B - 3.3.4 | Assess current use and operational readiness for intraday or same-day repos as liquidity tools. | N/A |  |  | X | X | X | X
|  | A-3.3.5 | Diagnosis of the degree of automation in recalls and SFT flows | B - 3.3.6 | Diagnose automation levels in recalls and SFT flows to mitigate settlement failure risk under T+1. | N/A |  | X |  |  | X |  | X
|  | A-3.3.6 | Analysis of the use of new tools for triparty and auto-borrowing operations | B - 3.3.5 | Evaluate triparty and autoborrowing arrangements for technological integration, efficiency, and alignment with T+1 speed and automation needs. | N/A |  |  | X |  | X | X | X
| B - Definition of operational and technical requirements | B - 3.3.1 | Redesign of the recall operational flow | N/A | Redesign recall workflows to ensure timely execution and avoid T+1 settlement failures, with clear responsibilities and early alerts. |  |  | X |  |  | X | X | X
| Definition of operational and technical requirements | B - 3.3.2 | Implementation of automated tools for the management of recalls | N/A | Implement automated tools for recall management integrated with custody and settlement systems, enabling real-time electronic communication. | SF-01 |  | X |  |  | X |  | X
| Definition of operational and technical requirements | B - 3.3.3 | Optimization of the allocation process and replacement of collateral | N/A | Optimize collateral allocation and substitution through automation, eligibility rules, accelerated replacement, and intraday margin management. | SF-02 |  | X | X | X | X | X
| Definition of operational and technical requirements | B - 3.3.4 | Strengthening capacities to operate with repos intraday or with settlement in T | N/A | Enhance readiness for intraday or same-day repos as liquidity tools, ensuring alignment with T+1 settlement timelines. | SF-02 |  |  | X | X | X | X
|  | B - 3.3.5 | Assessment and integration of triparty and autoborrowing solutions | N/A | Assess and integrate triparty and autoborrowing solutions for efficiency, scalability, and automated collateral access. | SF-02 |  |  | X |  | X | X | X
| Definition of operational and technical requirements | B - 3.3.6 | Review of cut-offs and redistribution of operational tasks | N/A | Review internal cut-offs and redistribute operational tasks to ensure intraday coverage and responsiveness under T+1. | SF-03 |  | X | X |  | X | X | X
| C -Implementation | C - 3.3.1 | Align the operational cycle of SFTs with T+1 | B - 3.3.6 | Review repo, loan, and triparty transaction cycles to ensure compatibility with the new T+1 framework, synchronizing execution, allocation, and settlement dates with securities market flows. | N/A | X | X |  |  | X | X | X
|  | C - 3.3.2 | Redesign the operational flow of recalls and returns | B - 3.3.1 | Standardize and advance the processes for requesting and returning borrowed securities, ensuring their activation on T and their smooth settlement on T+1 through coordinated and automated flows. | N/A |  | X |  |  | X | X | X
|  | C - 3.3.3 | Automate recalls and end-to-end SFT operational flows | B - 3.3.2 | Implement straight-through processing (STP) tools for recalls, returns, and pre-matching, reducing manual intervention and integrating trading, custody, and triparty systems. | N/A |  | X |  |  | X |  | X
|  | C - 3.3.4 | Optimize and automate collateral management | B - 3.3.3 | Improve collateral allocation, replacement, and release to avoid T+1 sales blockages by incorporating automatic rules and triparty or self-collateralization solutions. | N/A |  | X | X | X | X | X
|  | C - 3.3.5 | Strengthen intraday and T-settlement repo capabilities | B - 3.3.4 | Develop the ability to execute intraday or same-day (T) repos to provide immediate liquidity in the event of recalls or needs arising from the T+1 cycle. | N/A |  |  | X | X | X | X
|  | C - 3.3.6 | Integrate triparty, auto-borrowing, and auto-collateralization solutions | B - 3.3.5 | Connect and integrate triparty tools and auto-borrowing mechanisms in custodians and (I)CSDs, allowing temporary securities or cash shortfalls to be covered and adapting to the new T+1 cut-offs. | N/A |  |  | X |  | X | X | X
|  | C - 3.3.7 | Improve the SFT settlement model (STP, hold & release, partial) | B - 3.2.3 B - 3.2.6 | Adopt advanced settlement mechanisms such as hold & release, partial settlement, and netting, and clearly identify SFT transactions to reduce failures and increase post-trade efficiency. | N/A |  | X | X |  | X | X
|  | C - 3.3.8 | Redefine cut-offs and redistribute operational tasks | B - 3.3.6 | Establish a single calendar that integrates SFTs, cash, and collateral adjusted to T+1 deadlines, redistributing functions and operational shifts to cover critical recall, allocation, and settlement windows. | N/A |  | X | X |  | X | X | X
|  | C - 3.3.9 | Strengthen SFT data governance and quality | B - 3.3.1 B - 3.3.2 B - 3.3.3 B - 3.3.4 B - 3.3.5 B - 3.3.6 | Create a high-quality data framework for SFTs, with up-to-date SSIs, eligibility parameters, and clear links between transactions and collateral, ensuring consistency across all systems. | N/A |  | X |  |  | X | X | X
|  | C - 3.3.10 | Establish a model for governance and coordination between entities | B - 3.2.1 B - 3.2.5 B -3.2.6 | Define governance structures, service level agreements (SLAs), and performance metrics (KPIs) between lenders, custodians, triparty agents, and buy-side entities, ensuring coordination and adequate response times. | N/A |  | X |  |  | X | X | X
|  | C - 3.3.11 | Update contractual and operational documentation | B - 3.2.5 B - 3.2.6 | Review GMRA/GMSLA contracts, triparty agreements, and operating manuals to reflect new deadlines, automated processes, and responsibilities arising from the transition to T+1. | N/A |  |  |  |  | X | X | X
4. ASSET MANAGEMENT | A - GAP Analysis | A - 4.1.1 | Development of the process taxonomy | B - 4.1.1 | Identify and classify all processes within the entity's value chain. | N/A |  | X |  |  | X |  | X
| GAP Analysis | A - 4.1.2 | Identification of the affected taxonomy processes | B - 4.1.2 | Identify those processes that are directly related to and impacted by the T+1 settlement. | N/A |  | X |  |  | X |  | X
| GAP Analysis | A - 4.1.3 | Evaluation of current systems | B - 4.1.3 | Review features, automation levels, third-party integrations, and processing times | N/A | X | X |  |  | X |  | X
| GAP Analysis | A - 4.1.4 | Identification of the affected documentation | B - 4.1.4 | Review and locate all documentation, both internal and contractual, that will be impacted by the transition to T+1. | N/A |  |  |  |  | X | X | X
| GAP Analysis | A - 4.1.5 | Company reorganization | B - 4.1.5 | Identify and assess whether the necessary capabilities, sizing and resources are in place. | N/A |  | X |  | X |  |  | X
| B - Definition of operational and technical requirements | B- 4.1.1 | Definition of requirements for sending settlement instructions in T | N/A | Define the requirements necessary to ensure that corporate transactions and actions are received, confirmed and sent to the depository within the same trading day (T) | AM-01 | X | X |  |  |  | X | X
| Definition of operational and technical requirements | B- 4.1.2 | Definition of requirements for the selection of intermediaries | N/A | Establish the necessary mechanisms for selecting and monitoring intermediaries, including internal metrics, timely settlements, efficiency, etc. | AM-01 | X |  |  |  |  | X | X
| Definition of operational and technical requirements | B- 4.1.3 | Defining requirements to increase automation in portfolio management | N/A | Establish the necessary requirements to reduce manual intervention in the portfolio management process, from execution to settlement, and in communication with brokers, custodians, and counterparties | AM-01 | X | X |  |  | X
| Definition of operational and technical requirements | B- 4.1.4 | Defining requirements for updating documentation | N/A | Identify operational and contractual documentation impacted by the transition to T+1 within the entity and establish the necessary requirements for updating it | [5 empty] | X | X | X
| Definition of operational and technical requirements | B- 4.1.5 | Defining requirements for other support areas | N/A | Identify and formalize operational and organizational needs, including the restructuring of functions and resources. | AM-01 |  | X |  | X |  |  | X
| C - Implementation | C - 4.1.1 | Systems, Automation and Operartions | B- 4.1.1 | Upgrade OMS/PMS and Middle Office systems to enable the automatic and validated issuance of settlement instructions on T. Integrate matching tools (CTM, ALERT, SWIFT) and monitoring dashboards to ensure real-time instruction transmission and confirmation. | N/A | X | X |  |  |  | X | X
|  | C - 4.1.2 | Intermediary Selection and Connectivity | B- 4.1.2 | Assess the T+1 operational readiness of brokers and custodians, update contracts and SLAs with new confirmation deadlines, verify FIX/SWIFT connectivity, and establish structured communication and escalation channels. | N/A | X |  |  |  |  | X | X
|  | C - 4.1.3 | Portfolio and Order Management Automation | B- 4.1.3 | Configure intraday auto-allocation rules, integrate OMS/PMS systems for immediate post-trade confirmation, automate compliance checks, and provide real-time visibility of portfolio positions and liquidity. | N/A | X | X |  |  | X
|  | C - 4.1.4 | Treasury, FX and Liquidity Management | B- 4.1.5 | Review FX and cash flows, implement auto-FX or standing instructions, synchronise multi-currency settlements, define pre-funding policies, and automate balance and cash forecasting controls. | N/A |  | X | X | X | X
|  | C - 4.1.5 | Corporate Actions, Securities Lending and Collateral | B- 4.1.5 | Coordinate with custodians on calendar alignment and buyer protection adjustments, automate corporate event management, review securities lending and collateral agreements, and synchronise daily recall and margin movements. | N/A |  | X | X |  | X | X
|  | C - 4.1.6 | Documentation and client communication | B- 4.1.4 | Update legal and operational documentation with T+1 references, adapt forms and SSIs to STP processes, and communicate new deadlines and operational changes to clients. | N/A |  |  |  |  | X | X | X
|  | C - 4.1.7 | Risk, compliance and reporting | B- 4.1.5 | Strengthen intraday risk controls, deploy automated alerting for operational incidents, review timing and content of regulatory reports, and ensure technical adaptation of compliance systems. | N/A |  | X |  | X | X |  | X
5.DOCUMENTATION MANAGEMENT | D - External contractual documentation | D - 5.1.1 | Review and update external contractual documentation | N/A | Identify and assess all contractual documents impacted by the transition to the T+1 settlement cycle, ensuring that settlement timelines, delivery commitments, and failure-management clauses align with the new ESMA regulatory framework. This includes reviewing explicit references to settlement periods, operational cut-off times, collateral delivery terms, and reconciliation obligations; updating contractual language to reflect the new standard settlement cycle, adjusting clauses related to penalties, guarantees, and service levels, and coordinating updates with clients and counterparties to guarantee operational feasibility. | N/A
| D - Internal process documentation | D - 5.1.2 | Adapt internal process documentation | N/A | Identify and analyze all operating manuals, procedures, workflows, SOPs, and system-related technical documentation impacted by the reduction of the settlement cycle, ensuring full alignment with T+1 deadlines and operational constraints. This includes detecting references to T+2, adjusting process diagrams and flowcharts, reviewing automation dependencies, redefining internal roles and responsibilities, assessing third-party process alignment, updating risk control and escalation procedures and validating revised processes through internal governance. | N/A
| D - Staff training and customer communication | D - 5.1.3 | Develop internal training and external communication plans | N/A | Identify all teams and roles requiring updated training on T+1 operational changes, and design targeted training materials and communication strategies to ensure internal readiness and external client alignment. This includes defining training objectives by function, preparing ad-hoc materials and simulations, scheduling training sessions, identifying affected customer communications, updating communication policies, adapting commercial and digital client-facing materials, enabling customer-service staff to manage inquiries, and documenting all training and communication actions delivered. | N/A
| D - Impact on service level agreements (SLAs) and KPIs | D - 5.1.4 | Review of existing affected SLAs, update and incorporate KPIs | N/A | Review existing service commitments, response times, operational metrics, and monitoring frameworks to ensure alignment with the reduced timeframe required under the new ESMA regulation. This includes adjusting SLA commitments for execution, confirmation, and incident resolution; renegotiating timelines with custodians, suppliers, platforms, and other counterparties; redefining KPIs such as same-day instruction transmission rates or settlement efficiency; updating monitoring tools to detect deviations in real time; and documenting all changes for auditability and regulatory compliance. | N/A
Roadmap T+1 Spanish market | Activities detail
In collaboration with
Analysis GAP
Definition of operational and technical requirements
Implementation
ESMA RTS Amend - Final Report On Amendments to the RTS on Settlement Discipline

## 3. EU Recommendations
Support table
HIGH-LEVEL ROADMAP TO T+1 SECURITIES SETTLEMENT IN THE EU
Topic | ID | Name of Recommendation | Recommendation | Who | When | Final Report On Amendments to the RTS on Settlement Discipline
Trading Phase | TR-01 | TR-01 – End of day signal from TVs to CCPs | To facilitate settlement in the first settlement window, trading platforms and their CCP(s) should review End of Day processes. This includes optimising the timing of transaction netting, prompt transmission of settlement instructions to the relevant CSD(s), and timely delivery of required reports to clearing members. | Trading Venues, CCPS | End of 2026 | NA
| TR-02 | TR-02 – Trading venues' rulebooks | The Committee recommends that trading venues (of all asset classes) update and reconcile their rulebooks in accordance with their T+1 obligations (e.g. ex-dates, cancellations, etc). | Trading Venues | End of 2026 | NA
| TR-03 | TR-03 – Liquidity | The Committee recommends ongoing discussions to monitor liquidity impacts in a T+1 settlement context. Additionally, it advises continuous analysis and monitoring of developments both in the leadup to T+1 and after its implementation. | EU T+1 Industry Committee | October 2027 (pre-and post- go-live date) | NA
| TR-04 | TR-04 – Recall and Return Framework for SFTs |  |  |  | NA
| TR-04.1 | TR-04.1 – Standardised recall request deadline | Adopt a standardised recall notification request deadline, of 17:00 on Trade Date (T) | Trading Parties (involved in securities lending) | October 2027 | NA
| TR-04.2 | TR-04.2 – Standardised return notifications deadline | Set the notification deadline for recalls and returns at 30 minutes before the return settlement deadline i.e., 15:00, on T+1 as a best practice approach. N.B.: if DvP cutoff time becomes 17:00, the notification deadline will then move to 16:00. | Trading Parties (involved in securities lending) | October 2027 | NA
| TR-04.3 | TR-04.3 – Standardised return settlement deadline | Set the return settlement deadline for recalled securities at 30 minutes before the T2S DvP cutoff (i.e., 15:30) on T+1. N.B.: if DvP cutoff time becomes 17:00, the settlement deadline will then move to 16:30. | Trading Parties (involved in securities lending) | October 2027 | NA
| TR-04.4 | TR-04.4 – Adoption of ERCC best practice for termination of open repo | On the repo side, a similar question arises in relation to the notification for terminating open repo. Firms are encouraged to follow the relevant deadlines recommended by the ERCC for repo transactions . | Trading Parties (involved in repo) | October 2027 | NA
| TR-05 | TR-05 – Automatic shaping of settlement instructions | Automatic shaping of settlement instructions should be introduced in line with existing market practice (50 million nominal value in EUR, GBP and USD). This should apply at the trading level (i.e. after trade execution) and should cover both repo and cash bond trades, whether on-venue or OTC. For securities lending transactions shaping should remain optional. Collateral realignments and other FoP collateral movements should not be subject to automatic shaping | Trading venues, trading parties | October 2027 | NA
Matching and Confirmation | MC-01 | MC-01 – Promote the Standardised Electronic Exchange of Trade Allocations and Confirmations | Firms are strongly encouraged to adopt electronic standardised communication methods for the exchange of allocations and confirmations to support straight-through processing (STP). | Trading Parties, Settlement Intermediaries | End of 2026 | 3.2 Means for sending allocations and confirmations 3.3 The use of international open communication procedures and standards for messaging and reference 3.5 Allocations: alignment with settlement instructions’ matching fields data to exchange allocations and confirmations
| MC-02 | MC-02 – Intraday Transmission of Allocations and Confirmations, no later than 23:00 | Allocations and confirmations should be communicated intraday and as close to real time as operationally feasible. At a minimum, they should be exchanged no later than 23.00 on Trade Date, allowing buy-side firms and executing brokers one hour to send settlement instructions to their custody and Settlement Intermediaries before the start of settlement processes | Trading Parties, Settlement Intermediaries | End of 2026 | 3.1 Timing of allocations and confirmations
| MC-03 | MC-03 – Provision of PSET Data at the Point of Allocation | The delivery of PSET (Place of Settlement) data at the point of allocation is required to ensure the early identification of discrepancies and necessary realignments. | Trading Parties, Settlement Intermediaries | As soon as practicable | 3.6 Allocations: PSET as mandatory field
| MC-04 | MC-04 – Establishment of Industry to agree standard for SSI management and exchange | The Committee highlights the opportunity to deepen industry-level work on the standardisation exchange and maintenance of SSIs. Agreement on the necessary elements is essential for the establishment of a uniform rule and content across all stakeholders in the EU, UK and Swiss markets. The Committee intends to establish an expert task force, comprising representatives from all types of industry participant, with the mandate to review existing market standards (e.g., FMSB) and available functionalities to devise EU market standards for populating, sharing and storing SSIs. | EU T+1 Industry Committee | Q3 2025 | 3.4 Provision of professional clients’ reference data for allocations and confirmations and format
| MC-05 | MC-05 – Standardisation of Pre-Matching for SFTs
| MC-05.1 | MC-05.1 – Pre-matching (securities lending) | Require automated pre-matching of all Securities Lending instructions on Trade Date. This should include an SSI comparison as part of the overall pre-matching focus. For repo transactions, it is acknowledged that pre-matching can help in certain scenarios. However, it is more crucial for firms to automate the process for sending and checking confirmations and, where necessary, initiating selective affirmations to avoid any unnecessary delays. | Trading Parties (involved in securities lending) | 2027-10-01 | NA
| MC-05,2 | MC-05.2 – Trade confirmations (repo) |  | Trading Parties (involved in repo) | 2027-10-01 | NA
Clearing Phase | CL-01 | CL-01 – CCP process timings | For cash equity, CCPs should provide their trading day gross trade information, wherever applicable, Netting Report, and Settlement Instructions to their Clearing Members and Settlement Agents as soon as possible following the close of their last cleared trading venue(s)/platform(s). The target is within 30 minutes, considering the start time of the settlement process of the respective securities settlement system. | CCPs | 2027-10-01 | NA
| CL-02 | CL-02 – Clearing Member, Settlement Agent, Broker-dealers process timings | For cash equity, Clearing Members, Settlement Agents and Broker-Dealers should compress their own clearing processes as much as possible to ensure they have performed the following processes prior to the start of settlement: • Reconciliation & inventory management • Record creation & sending/releasing of settlement instructions. | Clearing Members, Settlement Agents, Brokers-Dealers | 2027-10-01 | NA
Settlement Phase | ST-01 | ST-01 – Instruction Management
| ST-0.1.1 | ST-01.1 – Real-time processing of settlement instructions | Market participants should instruct settlements continuously throughout the trading day facilitating intraday exception management of any settlement matching issues on Trade Date. Instructions should be submitted to Security Settlement Systems no later than 23:59 on Trade Date. • Overall aim: To the greatest extent possible, T+1 instructions/transactions should be instructed and matched at (I)CSD level before the start of the settlement cycle. Where required, the ‘Hold’ functionality should be used to facilitate timely instruction and matching. • Trading Parties: Settlement instructions should be processed in real-time after allocation / confirmation / trade booking. This will ensure sufficient time to cascade instructions through the chain of custody to the (I)CSDs for matching or identification and resolution of mismatches before the start of the settlement process. • Securities lending participant: Where the instructing party is a securities lender/borrower, settlement instructions should be sent to the settlement agent / (I)CSD without delay to enable matching at the (I)CSD ahead of instruction close / settlement cutoff where relevant (noting that SFTs will not necessarily follow the same T+1 convention as cash market trades). • CCP: Where the instructing party is a CCP, settlement instructions should be transmitted to the settlement agent / (I)CSD within a reasonable timeframe after the close of trading of their cleared venues, being early enough to reasonably enable counterparties to match at the (I)CSD prior to the start of the settlement window for such transactions. • CSDs / Custodians / Settlement Agents should support real-time instruction processing and settlement status messaging. Should this not be possible, sufficient ‘batches’ should be established to ensure that instruction, matching and settlement are not delayed. | Trading Parties, Settlement Intermediaries | October 2027 | 3.12 Real-time gross settlement and/or settlement batches
| ST-0.1.2 | ST-01.2 – Automated / STP instruction processing | All post-trade actors should support automated/STP instruction processing, eliminating fax and other non-standard / automated processes. | Trading Parties, Settlement Intermediaries | 2027-10-01 | 3.8 Settlement instructions: timing for sending settlement instructions (SIs) to a securities settlement system (SSS)
| ST-0.1.3 | ST-01.3 – Establish an Industry Taskforce to develop a single ‘gold standard’ format for settlement instructions - NA | The Committee highlights that an Industry Taskforce, comprising representatives of the SMPG, (I)CSDs, Settlement Intermediaries and SWIFT, will be established in Q3 2025 to identify the technical issues and recommend change requests where required. Once the standard is finalised, it will require wide adoption of the agreed format by all market participants and (I)CSDs is required, at a date to be determined depending on what changes are required. | EU T+1 Industry Committee | Q3 2025 | NA
| ST-0.1.4 | ST-01.4 – Custodians to offer PSAF information in Statement of Holding | Custodians to include PSAF information in Statement of Holding reporting to clients to provide transparency on depot location and enable accurate allocation by trading parties. | Custodians | End of 2026 | 5 Additional tools to improve settlement efficiency (good practice)
| ST-0.1.5 | ST-01.5 – Use of dynamic cash and stock forecasting tools | To optimise the management of resources, trading parties and Settlement Intermediaries should use automated tools to forecast funding and position needs (including borrowing and realignments), preferably on an intraday basis. | Trading Parties, Settlement Intermediaries | October 2027 | NA
| ST-0.1.6 | ST-01.6 – Use of Transaction type identifier in settlement instructions | SFTs and other transaction types need to be identified at settlement level by ensuring complete and consistent use of the existing “transaction type” field in settlement instructions. • Market participants and (I)CSDs should agree on a consistent and clear best practice guidance for using the field based on the existing ISO transaction types available today • All market participants and intermediaries should follow the guidance and use the field consistently to correctly represent the transaction that has been traded or instructed (should it be a post-trade administrative instruction) • FMIs and Settlement Intermediaries should support the transaction types identified in the best practice guidance to cascade their client’s instructions as instructed • AMI-SeCo should consider whether and how to support the Committee in conforming with this requirement and ongoing adherence post 11th October 2027 | Trading Parties, Settlement Intermediaries | End of 2026 | 3.7 Allocations and settlement instructions: transaction type
| ST-02 | ST-02 – Securities Settlement System Timings
| ST-02.1 | ST-02.1 – SSS Opening | Securities settlement systems should open for settlement at the latest by 00:00 on SD and the first batch settlement in T2S should run at 0:00, with the same priority order as today. Settlement instructions received by securities settlement systems after this time will still be submitted for settlement in subsequent cycles. | (I)CSDs and NCBs | October 2027 | NA
| ST-02.2 | ST-02.2 – SSS Closing: Establish a DvP cutoff of 16:00 for standard settlement in EUR and a FoP cutoff of 18:00 | NA | (I)CSDs and NCBs | October 2027 | NA
| ST-02.3 | ST-02.3 – SSS Closing: Alignment of non-EUR currencies to DvP cutoff of 16:00 | NA | (I)CSDs and NCBs | October 2027 | NA
| ST-02.4 | ST-02.4 – SSS Closing: Explore the potential establishment of a DvP cutoff of 17:00 | The Committee recommends completing additional analysis for a possible future extension of DvP cutoff to 17:00 by the end of 2025. This analysis should assess the feasibility for all market participants, including FX, Securities Lending, Funding & Treasury Desks, considering different cutoffs for EUR, DKK and other EU currencies as well as other services offered by CSDs, and TARGET Services (i.e. T2, TIPS, T2S, ECMS). Upon completion of the analysis, if the conclusion is to move the DvP cutoff to 17:00, a timeframe for implementation will be determined. Further details will be provided to the industry, noting that implementation will likely be post 11th October 2027. | (I)CSDs and NCBs | End of 2025 | NA
| ST-02.5 | ST-02.5 – Interaction with other global regions | Consider the needs of interaction with other global regions when changing settlement windows in Europe | CSDs, Settlement, intermediaries | October 2027 | NA
| ST-03 | ST-03 – Tools and Functionalities
| ST-03.1 | ST-03.1 – Partial settlement functionality (I)CSDs | Partial settlement functionality, including partial release, should be provided by all (I)CSDs without any exception. | (I)CSDs | October 2027 | 3.10 Auto-Partial settlement
| ST-03.2 | ST-03.2 – Partial settlement functionality (Intermediaries) | Partial settlement functionality, including partial release, should be supported by all intermediaries to allow the instructing party use of the functionalities | Settlement Intermediaries | 2027-10-01 | NA
| ST-03.3 | ST-03.3 – Establish Industry Taskforce to develop Partial Settlement Market Practice | The Committee highlights the importance of developing a market practice mandating use of partial settlement as a default, except for specific and well-documented use cases. It also emphasises examining factors which may hinder the wide-spread adoption of partial functionalities. | EU T+1 Industry Committee | Q3 2025 | NA
| ST-03.4 | ST-03.4 – Inclusion of partial settlement window in the first cycle of T2S NTS (C1SX) | To take advantage of partial settlement as soon as possible during the settlement process, it is proposed to introduce an additional partial settlement window in the first cycle of T2S NTS. Currently there is a partial settlement window only in the second cycle of T2S NTS. | T2S | End of 2026 | NA
| ST-03.5 | ST-03.5 – Hold & Release functionality - (I)CSDs | Hold & Release functionality to be provided by all (I)CSDs without any exception | (I)CSDs | October 2027 | 3.9 Hold & Release
| ST-03.6 | ST-03.6 – Hold & Release functionality – Intermediaries | Hold & Release functionality should be supported by all intermediaries to allow the instructing party, Clearing Member, or Settlement Agent to utilise these functionalities. | Settlement Intermediaries, CCPs | October 2027 | NA
| ST-03.7 | ST-03.7 – Intermediaries use of ‘Hold & Release’ | In cases where resources (Cash / Stock) are not yet in place, if required Settlement Agents and Custodians should use the ‘Hold’ functionality to enable early (I)CSD level matching and issue/exception identification and resolution. | Settlement Intermediaries, Clearing Members | October 2027 | NA
| ST-03.8 | ST-03.8 – Allegements - (I)CSDs | (I)CSDs should support the identification and reporting of allegements without any exception. | (I)CSDs | October 2027 | NA
| ST-03.8a | ST-03.8a – Allegements (Intermediaries) | Settlement Intermediaries should support the identification and reporting of allegements without exception | Settlement intermediaries | October 2027 | NA
| ST-03.9 | ST-03.9 – POA Functionality | POA functionality, including instruction of ‘already matched’ where applicable, should be provided by all (I)CSD and Settlement Agents without any exception. This includes T2S already matched POA services being offered by CSDs to both DCP & ICPs | (I)CSDs, CCPs, Clearing Members, Settlement Agents | October 2027 | NA
| ST-03.10 | ST-03.10 – Liquidity Tools & Functionalities | Exploration of existing functionalities and tools offered by (I)CSDs, NCBs and Settlement Intermediaries which support efficient liquidity management. | (I)CSDs, NCBs, Settlement Intermediaries | End of 2025 | NA
| ST-03.11 | ST-03.11 – Timely processing of transactions in non-EU currencies | Trades in currencies such as APAC, Middle East and ZAR currencies should be booked promptly after execution. In combination with intraday trade and settlement level matching, this will enhance the ability to meet funding deadlines. | Trading parties | End of 2026 | NA
| ST-03.12 | ST-03.12 – Auto-borrowing facilities | (I)CSDs and intermediaries are encouraged to offer auto-borrowing functionality to their clients where feasible. Where they have access to the service, participants are encouraged to sign up as borrowers to auto-borrowing or automatic pool lending facilities and, where practicable, to sign up as lenders. | (I)CSDs, Settlement Intermediaries, Trading Parties | October 2027 | NA
| ST-03.13 | ST-03.13 – Maximising bilateral and multilateral netting | Parties are encouraged to cooperate to maximise both bilateral and multilateral netting, including greater use of pair-offs to reduce settlement cost and risk. To avoid delays arising from the time needed to agree pair-offs, Trading Parties and their intermediaries should aim to standardise and automate this process as much as possible. This includes devising cross-industry market practice and standards, leveraging the ERCC’s pair-off template, which applies to both internal process (manual or automated) and third-party services | Trading parties, Settlement Intermediaries | October 2027 | NA
| ST-03.14 | ST-03.14 – Auto-collateralisation facilities | Auto-collateralisation facilities should be made available to all market participants to support intraday liquidity provision, either through the relevant CSDs or intermediaries. The recommendation applies to T2S auto-collateralisation, as well as equivalent tools provided by non-T2S CSDs or Settlement Intermediaries. | CSDs, Settlement Intermediaries | October 2027 | 3.11 Auto-collateralisation
Asset Management | AM-01 | AM-01 – Settlement cycles for funds’ units | Investment management firms should aim to reduce settlement cycles for subscriptions and redemptions of investment funds units to T+2 while at the same time retaining sufficient flexibility where needed and not penalising investment funds where transitioning to T+2 settlement is not feasible (e.g., for distribution or operational considerations) | Investment management companies | October 2027 | NA
| AM-02 | AM-02 – Cash breaches | Regulatory clarification should be provided to ensure that cash breaches caused by settlement misalignment are categorised as passive and non-reportable. Such clarification should lead to a consistent and harmonised interpretation across the EU/EEA of the deposit and borrowing limit rules to be applied at the Member State NCA level.Regulatory clarification should be provided to ensure that cash breaches caused by settlement misalignment are categorised as passive and non-reportable. Such clarification should lead to a consistent and harmonised interpretation across the EU/EEA of the deposit and borrowing limit rules to be applied at the Member State NCA level. | EU T+1 Industry Committee (to seek regulatory guidance from ESMA, NCA level) | End of 2026 | NA
FX | FX-01 | FX-01 – FX Lifecycle | Market participants should consider in their planning how they will engage with custodian/third party providers to successfully execute foreign exchange (FX) transactions in time to ensure successful processing across the full FX lifecycle from trading to settlement. Key considerations include: • liquidity patterns for Czech Koruna (CZK), Polish Zloty (PLN), Romanian Leu (RON) andIcelandic Krona (ISK); • partial settlements of securities (and the potential increase in the frequency of this); • impact on FX requirements of late trading in other asset classes; and • the need or desire to allocate a securities trade as soon as possible. | FX Market Participants | As soon as practicable | NA
| FX-02 | FX-02 – Partial Settlement | Market participants should consider and review with custodian/third party providers the potential increase in the partial settlements of securities and how this could impact decisions regarding how and when to fund FX requirements, keeping in mind the goal of reducing FX settlement risk | FX Market Participants | As soon as practicable | NA
| FX-03 | FX-03 – Settlement Risk | For any FX trades settling outside of PvP mechanisms, FX Market Participants will need to review their practices to reduce FX settlement risk in line with the FX Global Code. | FX Market Participants | Ongoing | NA
| FX-04 | FX-04 – PvP Mechanism | Market participants will need to continue engagement with custodians and complete assessment of instruction methods (e.g., cutoff alignment after EU market closes, functions available to accommodate currency holidays, etc.). CLS is expected to continue assessment of any impact on settlement risk reduction via CLS from shortened security settlement cycles. FX transactions must be dealt, processed, and submitted to CLS no later than 00:00 on settlement day (SD) to ensure their inclusion in the CLS settlement cycle. | FX Market Participants | Ongoing | NA
Corporate Events | CE-01 | CE-01 – Alignment of corporate event key dates with the T+1 standard settlement cycle | The period of time (“interval”) between the key dates of a corporate event are linked to the settlement cycle. Accordingly, the change in the standard settlement cycle from T+2 to T+1 will have an impact on the sequence of these key dates. It should be noted that the changes described below relate to changes in behaviour/systems rather than to the corporate event standards themselves: no changes to the standards are foreseen as the standards already link the sequence of corporate event key dates, as well as the length of the interval between key dates, to the standard settlement cycle). [more info in the Report] | Trading venues, CSDs and Settlement Intermediaries | October 2027 (interim milestones to be added) | NA
| CE-02 | CE-02 – Automation of buyer protection processing | Buyer protection is a process by which a buyer, who has yet to receive underlying securities subject to an elective corporate action, instructs its account provider/servicer in such a way as to receive the corporate action proceeds of his or her choice. Harmonised automated workflows for the processing of buyer protection instructions should be implemented with the view of T+1. | CSDs, Settlement Intermediaries | October 2027 (Timeline to be validated by September 2025) | NA
| CE-03 | CE-03 – Automation of market claims processing | A market claim is a process to reallocate the proceeds of a distribution to the contractually entitled party. Harmonised automated workflows for the processing of market claims should be implemented in view of T+1. | CSDs, Settlement Intermediaries | October 2027 (interim milestones to be added) | NA
Securities Financing Transactions | SF-01 | SF-01 – Settlement optimisation for SFTs | The transition to T+1 in the cash market means that a significant share of the repo market is expected to move to same day settlement (T+0). This presents significant risks and challenges in terms of intraday liquidity consumption and settlement efficiency. To mitigate these impacts, further measures are needed ahead of the T+1 implementation date to optimise SFT settlement. While this is subject to further discussion and analysis, the SFT workstream has identified the introduction of a batch settlement cycle during the day as a possible effective mitigating measure, ideally at 12:00. | (I)CSDs | October 2027 | NA
| SF-02 | SF-02 – Collateral and Loan Release Practices
| SF-02.1 | SF-02.1 – Pro-rata loan release practices | Formalise pro-rata loan release based on received collateral (covering both bilateral and triparty collateral) through the development of an industry best practice. |  | End of 2026 | NA
| SF-02.2 | SF-02.2 – Triparty RQV collateral tools and logic-based models | Promote use of triparty RQV collateral tools and logic-based models to support real-time loan release and reduce manual dependencies through the development of an industry best practice. |  | End of 2026 | NA
| SF-03 | SF-03 – Notifications from buy- side to lending intermediaries of sales | Buy-side participants to provide notification to lending intermediaries of any sales as soon as possible after execution to expedite any potential recalls within the cutoff times | Trading Parties (when selling securities) | October 2027 | NA
| SF-03.1 | SF-03.01 – Same-day returns for securities lending transactions | Advocate for greater use of same-day returns, subject to a 2-hour minimum buffer before settlement deadlines. | Trading Parties (Securities lending only) | End of 2026 | NA
| SF-03.2 | SF-03.02 – Automation of securities lending recalls and return instruction flows | Promote automation of securities lending recalls and return instruction flows using electronic messaging with defined data standards. | Trading Parties (Securities lending only) | End of 2026 | NA
Legal & Regulatory | LR-01 | LR-01 – National Specificities | National specificities may need to be addressed by impacted market participants or subjected to further monitoring or analysis (e.g., registered shares, shortening of the SEPA Direct Debit Core to D-0) to adapt to a T+1 environment. Although some issues might involve legal and regulatory changes at the national level, no specificities that would require modification of law, regulation or other guidance at EU level have been identified. Therefore, the technical workstream will continue to monitor and record any national specificities that would impact the shortening settlement cycle. In addition, some National Competent Authorities (NCAs) are engaging in discussions to identify all relevant specificities that would need to be addressed at the national level through legal and regulatory changes before the transition to T+1. It is also noted that to avoid misalignment among the 27 EU states and the 3 EEA states on the implementation date, the latter group of states should implement the same changes in their respective national laws according to the same timeframe as the EU. Currently there is no indication that any delay to EEA transposition is likely. | EU T+1 Industry Committee | Ongoing | NA
| LR-02 | LR-02 – Unharmonised insolvency protections | Review the opportunity to harmonise in the EU legal protections granted to settlement agents along the intermediary chain in case of insolvency, to create a harmonised protection environment for settlement. This analysis could be supported by comparative survey of the current state of play in each Member State. | Member States and European Commission | European Commission to conduct initial analysis based on feedback to consultation on capital markets integration | NA
B- 3.1.1.
B- 3.1.2, B- 3.1.5
GAP Analysis
|  |  | Synchronize FX and securities settlements |  | Align the processing of FX transactions with securities settlement cycles to ensure funds and securities are available for T+1 completion.
|  |  | Activate T+1 FX execution and adjust cut-offs |  | Enable FX execution on trade date (T) and redefine internal cut-offs to support timely settlement under T+1 conditions
|  |  | Automate FX booking, confirmation, and reconciliation |  | Implement full automation from trade capture to reconciliation to meet tighter T+1 operational timelines.
|  |  | Upgrade connectivity and architecture for PvP systems |  | Strengthen system integration with CLS and other PvP infrastructures to support faster, synchronized settlement processes.
|  |  | Deploy real-time intraday liquidity monitoring tools |  | Implement tools to track cash movements and liquidity needs in real time, ensuring sufficient funding for accelerated settlement.
|  |  | Implement intraday control and escalation procedures |  | Define controls and escalation paths to manage timing mismatches or liquidity shortfalls within the shortened T+1 cycle.
Roadmap T+1 Spanish market | Activities detail
In collaboration with